Australian Government,
Department of Infrastructure, Transport, Regional Development, Communications and the Arts

# Regional Connectivity Program (RCP) – Rounds 1 - 3 Rollout Update

**January 2025**

The Regional Connectivity Program (RCP) is delivering improved regional connectivity through the provision of mobile voice and data, fibre broadband, fixed wireless and community Wi-Fi solutions; supporting improved social and economic outcomes for regional and remote communities.

All projects funded under RCP Round 1 are currently scheduled to be completed by no later than 30 June 2025 and all projects funded under RCP Round 3 are currently scheduled to be completed by no later than 30 June 2027.

The tables below provide the status of projects funded under Round 1-3 of the program, with all forecast completion dates based on reporting provided by Grantee’s.

Project completion dates are estimated by grantees. The Australian Government does not have a direct role in project delivery, rather grantees are funded to complete the projects. Changes to project timelines are at the request of grantees. Grantees can at times experience unforeseen delays to the delivery of infrastructure projects, with potential delays including supply chain issues, adverse weather conditions, or to gaining various approvals that may be required. The Department regularly engages with Grantee’s to monitor the progress of each project and consider any requests for extension to support these delivery challenges.

The tables below also indicate the projects that have been removed from the program and will not be completed.

The Department works in partnership with Grantees to deliver approved projects that meet the program outcomes, and provide improved digital connectivity across regional, rural and remote Australia. Projects are typically removed from the program when grantees advise delivery of the project cannot be met within the program requirements and no other viable option can be provided.

There are a number of factors that can cause setbacks in the delivery of a project that may in some minor cases lead to a project not proceeding. This can include reasons such as:

* inability of the Grantee to obtain necessary land access or acquisition, planning approval or issues with integrating solutions into existing networks.
* increased costs associated with factors unknown to the Grantee at the time of application, often determined through initial mobilisation activities such as site surveys and engagement for approval requirements.
* change in availability of communication services in the locality since the grant was awarded.
* in very limited circumstances, the Commonwealth may remove a project from the program where a Grantee has not met contractual obligations associated with delivery obligations.

Table of contents

[Table 1: Regional Connectivity Program Round 1 Project Status 3](#_Toc185499174)

[Table 2: Regional Connectivity Program Round 2 Project Status 56](#_Toc185499175)

[Table 3: Regional Connectivity Program Round 3 Project Status 74](#_Toc185499176)

## Table 1: Regional Connectivity Program Round 1 Project Status

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Grantee | Project Name | Technology Type | Location | State | Project Description | RCP  Project Status | Actual / Expected Project Completion Date |
| CiFi Pty Ltd | Christmas Island - Top of the Mountain connectivity | Fixed Wireless Broadband | Christmas Island | External Territory of Australia | The project will extend CiFi’s existing fixed wireless network at the Settlement on Christmas Island to the residential area known as the ‘top of the mountain’. The network will provide improved broadband connectivity to the majority of residents and businesses in Christmas Island’s largest residential community, supporting the productivity of local businesses and enabling community access to telehealth, education and other essential digital services. | Complete | Q3, 2022 |
| Ace Internet Services Pty Ltd | Canyonleigh-Penrose Catchment Black Spot Connectivity: Tower 1 | Fixed Wireless Broadband | Canyonleigh | NSW | The project will deploy a fixed wireless broadband network in the Canyonleigh area of the Southern Highlands, near Sutton Forest. The network will support high definition video, data feed and communications for the Rural Fire Service and first responders in the Southern Highlands, as well as enabling the provision of high speed internet to areas of Canyonleigh and Sutton Forest. | Complete | Q1, 2022 |
| BullRoarer Networks Pty Ltd | Larras Lee & Boomey Fixed Wireless Network | Fixed Wireless Broadband | Larras Lee | NSW | The project will deploy a fixed wireless broadband and VoIP network in the communities of Larras Lee and Boomey, north of Molong. The network will enable the uptake of new agricultural and business technologies for local farms, as well as improving access to telehealth and education for residents. | Complete | Q2, 2022 |
| BullRoarer Networks Pty Ltd | Murrumbateman Fixed Wireless Network | Fixed Wireless Broadband | Murrumbateman | NSW | The project will deploy a fixed wireless broadband and VoIP network on the eastern side of Murrumbateman. The network will enable the uptake of new agricultural and business technologies for a number of wineries, as well as improving access to telehealth and education services for residents. | Complete | Q2, 2022 |
| Country Broadband Network Pty Ltd | Connecting the Outback | Fixed Wireless Broadband | Boggabilla | NSW | The project will extend Country Broadband Network's existing fixed wireless network in the Boggabilla area. The network will provide access to high-speed broadband connectivity for up to 400 people, enabling the uptake of new agricultural and business technologies and improving access to telehealth and education services. | Removed | - |
| Field Solutions Group | Regional Australia Network: Carathool | Fixed Wireless Broadband | Carathool | NSW | The project will deploy a fixed wireless network in the Carathool region of South Western NSW. The network will extend high-speed broadband connectivity into areas with limited existing coverage, enabling the uptake of new agricultural and business technologies in a crop growing and horticultural area. The project will also enable greater access to telehealth and education services. | Removed | - |
| Field Solutions Group | Regional Australia Network: Murrumbidgee | Fixed Wireless Broadband | Murrumbidgee | NSW | The project will deploy a fixed wireless network in the Murrumbidgee region, southwest of Leeton. The network will extend high-speed broadband connectivity into areas with limited existing coverage, enabling the uptake of new agricultural and business technologies for local irrigators and tourist providers and improving access to telehealth and education services. | Removed | - |
| Field Solutions Group Pty Ltd | Regional Australia Network: Bourke | Fixed Wireless Broadband | Bourke | NSW | The project will deploy a fixed wireless network in the Bourke region of North Western NSW. The network will extend high-speed broadband connectivity into areas with limited existing coverage, enabling the uptake of new agricultural and business technologies in an irrigated agriculture and wool growing area. The project will also enable greater access to telehealth and education services. | In Progress | Q2, 2025 |
| Field Solutions Group Pty Ltd | Regional Australia Network: Gunnedah | Fixed Wireless Broadband | Gunnedah | NSW | The project will deploy a fixed wireless network in the Gunnedah Shire and to neighbouring areas in the Liverpool Plains and Tamworth Regional Shires. The network will extend high-speed broadband connectivity into areas with limited existing coverage, enabling the uptake of new agricultural and business technologies in a high-value cotton, beef and broadacre cropping region and improving access to telehealth and education services. | In Progress | Q2, 2025 |
| Field Solutions Group Pty Ltd | Regional Australia Network: Leeton | Fixed Wireless Broadband | Grong Grong | NSW | This project has been rescoped and will now deploy a fixed wireless network in the township of Grong Grong. The network will extend high-speed broadband connectivity into areas with limited existing coverage. | In Progress | Q2, 2025 |
| Field Solutions Group Pty Ltd | Regional Australia Network: Moree | Fixed Wireless Broadband | Moree Plains | NSW | The project will deploy a fixed wireless network in the wider Moree region, including the towns of Mallowa, Bullarah, Pallamallawa, Gravesend, Collarenebri and North Star, as well as part of the Gwydir Highway. The network will extend high-speed broadband connectivity into areas with limited existing coverage, enabling the uptake of new agricultural and business technologies and improving access to telehealth and education services. | In Progress | Q2, 2025 |
| Field Solutions Group Pty Ltd | Regional Australia Network: Warren | Fixed Wireless Broadband | Warren | NSW | The project will deploy a fixed wireless broadband network in the Narromine-Warren region. The network will extend high-speed broadband connectivity into areas with limited existing coverage, enabling the uptake of new agricultural and business technologies in a significant cotton, grain and livestock region with development opportunities in tourism and manufacturing, and improving access to telehealth and education services. | In Progress | Q2, 2025 |
| NBN Co Limited | Connecting Costa Group – Growing the Guyra District and New England Region: New England Hwy | Fibre Broadband | Guyra | NSW | The project will upgrade the NBN access technology at the Costa Group hydroponic tomato glasshouse facility on the New England Highway at Guyra from Sky Muster Satellite to Fibre to the Premises. The upgrade will support expanded business operations at the facility, including in administration, research and horticultural production, with benefits to the local economy through increased employment opportunities and regional output. | Complete | Q1, 2023 |
| NBN Co Limited | Connecting Costa Group – Growing the Guyra District and New England Region: Elm St | Fibre Broadband | Guyra | NSW | The project will upgrade the NBN access technology at the Costa Group hydroponic tomato glasshouse facility at Elm Street, Guyra from Sky Muster Satellite to Fibre to the Premises. The upgrade will support expanded business operations at the facility, including in administration, research and horticultural production, with benefits to the local economy through increased employment opportunities and regional output. | Complete | Q1, 2023 |
| Telstra Limited | Mossgiel | Mobile Voice & Data | Mossgiel | NSW | The project will upgrade antenna equipment and backhaul capacity at the existing Telstra 3G base station in the community of Mossgiel to provide Telstra 4GX and Internet of Things coverage to the area and along the Cobb Highway. The upgrade will enable the adoption of farm and rural water management solutions to support the productivity of the agriculture sector, as well as improving access to telehealth, education and emergency communications. | Complete | Q2, 2023 |
| Telstra Limited | Oxley | Mobile Voice & Data | Oxley | NSW | The project will upgrade antenna equipment and backhaul capacity at the existing Telstra 3G base station at Oxley to provide Telstra 4GX and Internet of Things coverage to the town and surrounding areas. The upgrade will enable a range of smart farming and smart water management solutions to promote productivity in this area, as well as improving access to telehealth, education and emergency communications. | Complete | Q1, 2024 |
| Telstra Limited | Tooma | Mobile Voice & Data | Tooma | NSW | The project will deploy a Telstra 4GX macro cell base station in the Snowy Valleys community of Tooma. The new base station will enable the uptake of new agricultural and business technologies for livestock and dairy producers and local tourism operators, as well as improving access to telehealth, education and emergency communications. | Complete | Q3, 2023 |
| Wi-Sky NSW Pty Ltd | Cootamundra-Gundagai & Snowy Valleys Council Solution (CGSVCS) | Fixed Wireless Broadband | Cootamundra-Gundagai, Snowy Valleys | NSW | The project will deploy an extended fixed wireless network across the Cootamundra-Gundagai and Snowy Valleys regions. The network will provide high-speed residential and enterprise broadband services to communities across a wide area using an innovative, low-cost and disaster-resilient design suited to local conditions. | Complete | Q2, 2024 |
| Wi-Sky NSW Pty Ltd | Hilltops Council Regional Connectivity Solution (HCRCS) | Fixed Wireless Broadband | Hilltops | NSW | The project will deploy an extended fixed wireless network across the Hilltops region. The network will provide high-speed residential and enterprise broadband services to communities across a wide area using an innovative, low-cost and disaster-resilient design suited to local conditions. | Complete | Q2, 2024 |
| Wi-Sky NSW Pty Ltd | Upper Lachlan Rural Connectivity Solution (ULRCS) | Fixed Wireless Broadband | Upper Lachlan | NSW | The project will deploy an extended fixed wireless network across the Upper Lachlan region. The network will provide high-speed residential and enterprise broadband services to communities across a wide area using an innovative, low-cost and disaster-resilient design suited to local conditions. | Complete | Q2, 2024 |
| Field Solutions Group | Satellite Backhaul Broadband Services for NT Remote Communities | Satellite Broadband | Arawerr, Mungkarta, Gan Gan, Wandawuy | NT | The project will deploy a satellite backhaul broadband solution servicing the remote communities of Arawerr, Gan Gan, Mungkarta and Wandawuy. The service will provide pay-as-you-go broadband data to residents, enabling improved access to telehealth and education services. | Removed | - |
| NBN Co Limited | Yirrkala Satellite to Fibre to the Premise Technology Switch | Fibre Broadband | Yirrkala | NT | The project will upgrade the NBN access technology in the East Arnhem town of Yirrkala from Sky Muster satellite to Fibre to the Premises. The upgrade will support economic diversification opportunities in cultural tourism, creative industries and the health sector, as well as improving access to telehealth and education services. | Complete | Q4, 2023 |
| Telstra Limited | Ampilatwatja | Mobile Voice & Data | Ampilatwatja | NT | The project will upgrade the capacity of the existing Telstra 4GX macro cell base station in the Aboriginal community of Ampilatwatja. The new base station will provide improved mobile connectivity to support the uptake of new business technologies by local retailers, as well as enabling greater access to telehealth, education and other essential services. | Complete | Q4, 2024 |
| Telstra Limited | Arnhem Fibre Upgrade Project | Fibre Backhaul | Arnhem | NT | The project will upgrade core transmission equipment at Telstra sites across East Arnhem Land, increasing existing backhaul capacity between Darwin and Nhulunbuy from 5 Gbps to 100 Gbps. The project will also upgrade the capacity of the existing Telstra 4GX base station at Mount Saunders near Nhulunbuy. The upgrades will support business development opportunities and increasing data needs in a number of sectors, as well as improving access to telehealth, education services and public safety connectivity. | In Progress | Q2, 2025 |
| Telstra Limited | Small Cell Tower in Wilora | Mobile Voice & Data | Wilora | NT | The project will deploy a new Telstra 4GX-lite satellite small cell base station in the Aboriginal community of Wilora, in the Central Desert region. The new small cell will provide improved mobile connectivity to support economic opportunity in the region, as well as to enable greater access to telehealth, education, public safety communications and other essential services. | Complete | Q2, 2023 |
| Connected Farms Pty Ltd | Roma Datacentre and Regional Fixed Wireless Internet | Fixed Wireless Broadband | Roma | QLD | The project will deploy a fixed wireless network providing broadband coverage to the region south of Roma, as well as an edge datacentre to provide improved data management for agribusinesses in the region. This provides a significant uplift to connectivity in an agricultural area, enabling increased uptake of agtech and decision farming with benefits for productivity. The datacentre will also employ locally recruited and trained personnel. | Complete | Q1, 2022 |
| Dreamtilt Pty Ltd (Gladstone Auto Club) | Benaraby Motorsports Complex Telecommunication Project | Fixed Wireless Broadband | Benaraby | QLD | The project will deploy a fixed wireless network at the new Benaraby Motorplex. The network will provide high-speed broadband connectivity to the Motorplex and surrounding residential areas, enabling the new complex to host events attracting large numbers of tourists to the region and providing increased access to internet services for local residents. | Complete | Q4, 2022 |
| Field Solutions Group | Regional Australia Network: Mareeba | Fixed Wireless Broadband | Mareeba | QLD | The project will deploy a fixed wireless network in the wider Mareeba region, west of Cairns. The network will extend high-speed broadband connectivity into areas with limited existing coverage such as Petford and Chillagoe, enabling the uptake of new agricultural and business technologies and improving access to telehealth and education services. | Removed | - |
| Field Solutions Group Pty Ltd | Regional Australia Network: Balonne-Bollon | Fixed Wireless Broadband | Balonne | QLD | The project will deploy a fixed wireless network in the Balonne region, centred around the town of Bollon. The network will extend high-speed broadband connectivity into areas with limited existing coverage, enabling the uptake of new agricultural and business technologies for local livestock producers and improving access to telehealth and education services for residents. | Complete | Q2, 2024 |
| Field Solutions Group Pty Ltd | Regional Australia Network: Isaac | Fixed Wireless Broadband | Isaac | QLD | The project will deploy a fixed wireless network in the Isaac region. The network will extend high-speed broadband connectivity into areas with limited existing coverage, enabling the uptake of new agricultural and business technologies for local livestock producers, including a new beef processing plant, and improving access to telehealth and education services for residents. | In Progress | Q2, 2025 |
| Field Solutions Group Pty Ltd | Regional Australia Network: Napranum | Fixed Wireless Broadband | Napranum | QLD | The project will deploy a fixed wireless network in the town of Napranum. The network will enable the efficient delivery of essential services, such as health, education, public safety and cultural heritage initiatives, by the Napranum Aboriginal Shire Council. | In Progress | Q2, 2025 |
| Field Solutions Group Pty Ltd | Regional Australia Network: Paroo-Bulloo | Fixed Wireless Broadband | Paroo, Bulloo | QLD | The project will deploy a fixed wireless network in the Paroo and Bulloo Shires. The network will extend high-speed broadband connectivity into areas with limited existing coverage, supporting the uptake of new agricultural and business technologies, as well as providing improved communications along two significant tourist routes. | In Progress | Q2, 2025 |
| Field Solutions Group Pty Ltd | Regional Australia Network: Tambo | Fixed Wireless Broadband | Blackall-Tambo | QLD | The project will deploy a fixed wireless network in the Blackall-Tambo Shire region. The network will extend high-speed broadband connectivity into areas with limited existing coverage, supporting the uptake of new agricultural and business technologies, as well as enabling the effective provision of local medical services through telehealth options. | In Progress | Q2, 2025 |
| NBN Co Limited | Alpha Satellite to Fibre to the Premise Technology Switch | Fibre Broadband | Alpha | QLD | The project will upgrade the NBN access technology in the Barcaldine Shire town of Alpha from Sky Muster to Fibre to the Premises. The upgrade will support the operations of local businesses and community organisations, as well as improving access to telehealth and education services for residents. | Complete | Q1, 2023 |
| NBN Co Limited | Murweh Satellite to Fixed Line Technology Change: Augathella | Fibre Broadband | Augathella | QLD | The project will upgrade the NBN access technology in the Murweh Shire town of Augathella from Sky Muster satellite to Fibre to the Premises. The upgrade will support the operations of local businesses, increasing regional output and local employment, as well as improving access to telehealth and education services for residents. | Complete | Q1, 2023 |
| NBN Co Limited | Murweh Satellite to Fixed Line Technology Change: Morven | Fibre Broadband | Morven | QLD | The project will upgrade the NBN access technology in the Murweh Shire town of Morven from Sky Muster satellite to Fibre to the Premises. The upgrade will support the operations of local businesses, increasing regional output and local employment, as well as improving access to telehealth and education for residents. | Complete | Q1, 2023 |
| NBN Co Limited | Surat Satellite to Fibre to the Premise Technology Switch | Fibre Broadband | Surat | QLD | The project will upgrade the NBN access technology in the South West Queensland town of Surat from Sky Muster satellite to Fibre to the Premises. The upgrade will support growth opportunities in a number of sectors, particularly tourism, and will improve health, education and public safety connectivity in the community. | Complete | Q1, 2023 |
| Queensland Capacity Network Pty Ltd | QLD Central Highlands Project: Bluff | Fixed Wireless Broadband | Bluff | QLD | The project will deploy a fixed wireless network to the town of Bluff, in the Central Highlands of Queensland. The network will extend high-speed broadband connectivity to the town, benefiting local community facilities, small businesses and residents. | Complete | Q1, 2023 |
| Queensland Capacity Network Pty Ltd | QLD Central Highlands Project: Dingo | Fixed Wireless Broadband | Dingo | QLD | The project will deploy a fixed wireless network to the town of Dingo, in the Central Highlands of Queensland. The network will extend high-speed broadband connectivity to the town, benefiting local community facilities, small businesses and residents. | Complete | Q1, 2023 |
| Queensland Capacity Network Pty Ltd | QLD Central Highlands Project: Duaringa | Fixed Wireless Broadband | Duaringa | QLD | The project will deploy a fixed wireless network to the town of Duaringa, in the Central Highlands of Queensland. The network will extend high-speed broadband connectivity to the town, benefiting local community facilities, small businesses and residents. | Complete | Q1, 2023 |
| Telstra Limited | Aurukun | Mobile Voice & Data | Aurukun | QLD | The project will upgrade the transmission and backhaul capacity at the existing Telstra 4GX mobile base station at Aurukun, a remote Indigenous community located on Cape York in Queensland. The upgrade will support online banking and financial transactions at existing retail businesses, as well as supporting local employment opportunities. | Complete | Q4, 2022 |
| Telstra Limited | Cow Bay | Mobile Voice & Data | Buchanan Creek | QLD | The project will deploy a new Telstra 4GX macro cell base station in the Far North Queensland community of Cow Bay, located in the Daintree World Heritage Rainforest. The new base station will provide improved mobile connectivity to support the operations of tourism providers and local businesses in a popular tourist location. Increased mobile coverage will also enable efficiencies in council service delivery, access to telehealth and education services, and public safety communications in a cyclone and flood prone region. | Complete | Q2, 2024 |
| Telstra Limited | Dajarra | Mobile Voice & Data | Dajarra | QLD | The project will upgrade antenna equipment and backhaul capacity at the existing 3G Telstra base station in Dajarra, to provide Telstra 4GX and Internet of Things coverage to the town and surrounding areas. The upgrade will support the operations of local businesses and enable remote working opportunities in the area. | Complete | Q3, 2023 |
| Telstra Limited | Lake Moondarra | Mobile Voice & Data | Mount Isa | QLD | The project will deploy a new Telstra 4GX small cell base station to Lake Moondarra, the primary water supply facility for the Mount Isa region and an important social and recreation hub for the Mt Isa community. The new base station will enable improved tourism and retail services, water supply management, and public safety communications at the lake. | Complete | Q3, 2024 |
| Telstra Limited | Mornington Island | Mobile Voice & Data | Gununa | QLD | The project will upgrade the capacity of the existing Telstra 4GX mobile facility in the Indigenous community of Gununa on Mornington Island. The project will also upgrade the existing fibre network between Mt Isa and Point Parker, and deploy a new mobile site near Century Mine, to provide microwave backhaul capacity to the Mornington Island. The upgrades will support the delivery of government services, as well as health and education resources. Improved connectivity will also support expanded business opportunities in cultural and fishing tourism. | Complete | Q4, 2024 |
| Telstra Limited | Mt Coolon | Mobile Voice & Data | Mount Coolon | QLD | The project will upgrade the antenna equipment and backhaul capacity at the existing Telstra 3G base station in the Central West Queensland locality of Mt Coolon to provide 4GX mobile coverage. The upgrade will provide improved mobile connectivity to support the uptake of new agricultural and business technologies by the local cattle farming sector, as well as regional development opportunities in mining and freight. Increased mobile coverage will also enable greater access to public safety communications in a drought and cyclone risk area, as well as education and other essential services. | Complete | Q3, 2023 |
| Telstra Limited | Palm Island | Mobile Voice & Data | Palm Island | QLD | The project will upgrade the existing Telstra 4GX macro base station at Palm Island North. The upgrade will provide improved mobile capacity to support economic development opportunities on Palm Island, including in tourism, aquaculture and retail. Increased mobile connectivity will also enable improved access to telehealth, education, natural disaster warnings and other essential services for the community. | Complete | Q2, 2024 |
| Wi-Sky Queensland Pty Ltd | Etta Plains Station connectivity project | Fixed Wireless Broadband | Etta Plains | QLD | The project will deploy a fixed wireless broadband and public Wi-Fi coverage to the Etta Plains area near Julia Creek. The network will enable the uptake of new agricultural and business technologies for a number of cattle stations and irrigators, as well as improving emergency communications in a flood-plain area. | Complete | Q2, 2022 |
| Wi-Sky Queensland Pty Ltd | Wi-Sky QLD North West Queensland Connectivity Project: Julia Creek | Fixed Wireless Broadband | Julia Creek | QLD | The project will deploy a fixed wireless broadband and public Wi-Fi coverage along the Flinders Highway between Richmond and Julia Creek. The network will enable the uptake of new agricultural and business technologies for pastoral producers and retail providers, including local online retailers and business operators. Improved connectivity will also improve access to telehealth, education services and public safety communications. | Complete | Q4, 2022 |
| Wi-Sky Queensland Pty Ltd | Wi-Sky QLD North West Queensland Connectivity Project: Stamford | Fixed Wireless Broadband | Stamford | QLD | The project will deploy a fixed wireless broadband and public Wi-Fi coverage along the Flinders Highway between Richmond and Stamford. The network will enable the uptake of new agricultural and business technologies for pastoral producers and retail providers, including local online retailers and business operators. Improved connectivity will also improve access to telehealth, education services and public safety communications. | Complete | Q2, 2022 |
| NBN Co Limited | Lewiston East Fixed Wireless to Fibre to the Premise Technology Switch | Fibre Broadband | Lewiston East | SA | The project will upgrade the NBN access technology in the town of Lewiston East, north of Adelaide, from Fixed Wireless to FTTP. The upgrade will support anticipated population growth in the area, as well as supporting local economic growth and diversification opportunities. | Complete | Q2, 2023 |
| NBN Co Limited | Wudinna Satellite to Fixed Line Technology Change | Fibre Broadband | Wudinna | SA | The project will upgrade the NBN service technology in the town of Wudinna from NBN Sky Muster to NBN Fibre to the Premises. The upgrade will improve access to online education and health services, expand economic opportunities and increase connectedness and digital capabilities in the community. | Complete | Q2, 2023 |
| Telstra Limited | Ernabella | Mobile Voice & Data | Pukatja | SA | The project will upgrade the backhaul capacity to the existing Telstra 4G mobile tower in Ernabella (Pukatja). The upgrade will provide improved coverage and user throughput speeds for the Ernabella township and the surrounding community, including the local airstrip. | Complete | Q2, 2024 |
| Telstra Limited | Far North SA | Mobile Voice & Data | APY Lands, Leigh Creek, Hawker | SA | The project will upgrade key transmission infrastructure between Hawker and Leigh Creek in South Australia’s far north, expanding the available core network capacity into Leigh Creek and Marree. This will facilitate the provision of fixed broadband services to Leigh Creek Area School and Marree Aboriginal School. The project will also upgrade the transmission capacity at Telstra’s Mount Scott and Leigh Creek base stations, enabling improved 4G access. Telstra also will commission 4G Satellite Small Cells into the communities of Dalhousie Springs, Yunyarinyi, Nyapari, Murputja, Kalka, Kanpi and Watinuma. | In Progress | Q2, 2025 |
| Telstra Limited | Mintaro | Mobile Voice & Data | Stanley | SA | The project will upgrade the antenna equipment and backhaul capacity at the existing Telstra 3G base station in the Clare Valley community of Mintaro to provide 4GX mobile coverage. The upgrade will provide improved mobile connectivity to support the uptake of new agricultural and business technologies by the local agricultural and tourism sectors. Increased mobile coverage will also support lifestyle migration to the area by enabling greater access to telehealth, education and other essential services. | Complete | Q3, 2023 |
| FortyTwo 24 Pty Ltd | Enhancing Australia's Sovereign Space Capability | Fibre Backhaul | Melton Mowbray | TAS | The project will deploy an optical fibre extension between the Midlands Highway and Bisdee Tier to provide 10 Gbps data capacity to the Greenhill Observatory operated by the University of Tasmania. Improved connectivity at the Greenhill Observatory will allow UTAS and Tasmania to access applied commercial development opportunities in the burgeoning space industry, in partnership with government, local and international companies, and research agencies. This will assist to diversify the Tasmanian economy towards a high-value industry. | Complete | Q2, 2022 |
| NBN Co Limited | Geeveston Fixed Wireless to Fibre to the Premise Technology Change | Fibre Broadband | Geeveston | TAS | The project will upgrade the NBN access technology in the Huon Valley town of Geeveston from Fixed Wireless to Fibre to the Premises. The upgrade will support improved connectivity for a number of local industries, as well as for health centres and local schools. | Complete | Q1, 2023 |
| TasmaNET Pty Ltd | Connectivity Upgrade Tahune Airwalk and the Warra Ecosystem Observatory | Fixed Wireless Broadband | Geeveston | TAS | The project will upgrade the existing communications network servicing the Tahune Airwalk and Warra Ecosystem Observatory in southern Tasmania. The network will provide broadband connectivity to the highly popular Tahune Airwalk tourist attraction, enabling the provision of internet and VoIP services to guests and staff and improving public safety communications. A new communication service at the Warra Ecosystem Observatory will enable the facility to more efficiently collect and distribute ecological research data. | Complete | Q1, 2023 |
| Telstra Limited | Jericho | Mobile Voice & Data | Jericho | TAS | The project will upgrade antenna equipment and backhaul capacity at the existing 3G Telstra base station in Jericho to provide Telstra 4GX and Internet of Things coverage to the town and surrounding areas. The upgrade will enable increased commuter safety along a major transport route, as well as improving the attractiveness of the area as a tourist location. | Complete | Q3, 2023 |
| Telstra Limited | King Island | Mobile Voice & Data | King Island | TAS | The project will upgrade the telecommunications network on King Island by upgrading the microwave transmission link between Victoria and King Island to significantly increase capacity, as well as deploying several new 4G sites and upgrading existing mobile network facilities across the island to provide new and enhanced mobile services to residents and businesses. | Complete | Q1, 2024 |
| Telstra Limited | TAS Schools | Fibre Broadband | Wesley Vale, Bagdad, Dunally, Forest, Glen Huon, Molesworth, Nubeena, Yolla, Sheffield | TAS | The project will upgrade and extend wideband connectivity to nine regional schools in Tasmania. This will involve the extension of new fibre to the schools as well as core transmission capacity upgrades to enable high-speed data services. The upgrade will also provide broader improvements to Telstra services in each community. | Complete | Q2, 2023 |
| Field Solutions Group Pty Ltd | Regional Australia Network: Swan Hill | Fixed Wireless Broadband | Swan Hill | VIC | The project will deploy a fixed wireless network in the Swan Hill region. The network will enable the uptake of new agricultural and business technologies in a high-value irrigated farming area, as well as supporting local manufacturing and other diversification opportunities and improving access to telehealth and education. | In Progress | Q2, 2025 |
| NBN Co Limited | Fixed Wireless to Fibre to the Premises Technology Change: Birregurra | Fibre Broadband | Birregurra | VIC | The project will upgrade the NBN access technology in the Colac-Otway Shire town of Birregurra from Fixed Wireless to Fibre to the Premises. The upgrade will provide improved broadband connectivity to encourage migration to the area and to support the uptake of business technologies for the tourism, health and agriculture industries. Increased connectivity will also enable improved access to education and telehealth services in the community. | Removed | - |
| NBN Co Limited | Fixed Wireless to Fibre to the Premises Technology Change: Hopetoun | Fibre Broadband | Hopetoun | VIC | The project will upgrade the NBN access technology in the Southern Mallee town of Hopetoun from Fixed Wireless to Fibre to the Premises. The upgrade will provide improved connectivity to increase the economic competitiveness of the region and enable more efficient service delivery in the wider Southern Mallee area. | Complete | Q2, 2023 |
| NBN Co Limited | Fixed Wireless to Fibre to the Premises Technology Change: Murchison | Fibre Broadband | Murchison | VIC | The project will upgrade the NBN access technology in the Goulburn Valley town of Murchison from Fixed Wireless to Fibre to the Premises. The upgrade will provide improved connectivity to support local orchard, vineyard and dairy farm activities, as well as the delivery of health and education services to the community. | Complete | Q2, 2024 |
| NBN Co Limited | Fixed Wireless to Fibre to the Premises Technology Change: Rushworth | Fibre Broadband | Rushworth | VIC | The project will upgrade the NBN access technology in the Campaspe Shire town of Rushworth from Fixed Wireless to Fibre to the Premises. The upgrade will provide improved connectivity to support growth opportunities in tourism and health services, as well as increasing access to other essential services. | Complete | Q2, 2023 |
| NBN Co Limited | Fixed Wireless to Fibre to the Premises Technology Change: Teesdale | Fibre Broadband | Teesdale | VIC | The project will upgrade the NBN access technology in the Golden Plains Shire town of Teesdale from Fixed Wireless to Fibre to the Premises. The upgrade will provide improved connectivity to support population growth in the town, as well as enabling access to new agricultural, business and education and training technologies for local businesses and residents. | Removed | - |
| NBN Co Limited | Fixed Wireless to Fibre to the Premises Technology Change: Timboon | Fibre Broadband | Timboon | VIC | The project will upgrade the NBN access technology in the Corangamite town of Timboon from Fixed Wireless to Fibre to the Premises. The upgrade will provide improved connectivity to support growth opportunities in tourism and hospitality, as well as existing dairying, forestry and lime production operations. | Removed | - |
| NBN Co Limited | Kaniva Satellite to Fibre to the Premise Technology Switch | Fibre Broadband | Kaniva | VIC | The project will upgrade the NBN access technology in the West Wimmera town of Kaniva from Sky Muster to Fibre to the Premises. The upgrade will provide improved connectivity to support local agricultural and tourism businesses, as well as a number of community facilities providing health, education, post and emergency services to residents. | Complete | Q2, 2023 |
| Telstra Limited | Avenel | Mobile Voice & Data | Avenel | VIC | The project will upgrade the capacity of the existing Telstra 4G macro cell base station in the Strathbogie Shire town of Avenel. The upgrade will provide improved mobile connectivity to support the digital needs of residents and tourists, as well as enabling the uptake of agricultural technologies and improving public safety coverage along significant highways and rail lines. | Complete | Q1, 2023 |
| Telstra Limited | Avenel South | Mobile Voice & Data | Avenel South | VIC | The project will upgrade the capacity of the existing Telstra 4G macro cell base station located south of the Strathbogie Shire town of Avenel. The upgrade will provide improved mobile connectivity to support the digital needs of residents and tourists, as well as the development of local economic hubs and safety outcomes along two significant highways. | Complete | Q1, 2023 |
| Telstra Limited | Berriwillock | Mobile Voice & Data | Berriwillock | VIC | The project will deploy a new Telstra 4GX macro cell base station in the Mallee town of Berriwillock. The new base station will provide improved mobile connectivity to support the digital needs of residents, commuters and businesses, including the development of new opportunities in tourism as part of the Silo Art Trail. Increased mobile connectivity will also enable greater access to telehealth and other essential services, as well as public safety communications in a fire and flood prone area and along the Calder Highway. | Complete | Q2, 2023 |
| Telstra Limited | Bridgewater | Mobile Voice & Data | Bridgewater on Loddon | VIC | The project will deploy a new Telstra 4GX small cell base station in the community of Bridgewater on Loddon, north west of Bendigo. The new small cell will provide improved mobile connectivity to support the uptake of new agricultural and business technologies by local industries, as well as efficiencies in the supply chain along the Calder Highway. Increased mobile coverage will also support population growth by enabling greater access to telehealth, education and other essential services, as well as improving public safety communications in a flood prone area. | Complete | Q3, 2023 |
| Telstra Limited | Broughton | Mobile Voice & Data | Broughton | VIC | The project will deploy a Telstra 4G macro cell base station in the West Wimmera community of Broughton. The new base station will provide improved mobile coverage and capacity to support the uptake of new agricultural and business technologies in a mixed farming region, as well as enabling improved access to essential services including health, education and emergency communications. | Complete | Q4, 2023 |
| Telstra Limited | Cabbage Tree Creek | Mobile Voice & Data | Cabbage Tree Creek | VIC | The project will deploy a Telstra 4G small cell base station at Cabbage Tree Creek, located near Bairnsdale in East Gippsland. The new base station will provide improved mobile connectivity to support economic diversification opportunities in tourism, agriculture and performing arts, as well as increased access to essential services including health, education and emergency communications. | Complete | Q2, 2023 |
| Telstra Limited | Corack | Mobile Voice & Data | Corack East | VIC | The project will deploy a new Telstra 4GX macro cell base station in the Wimmera community of Corack. The new base station will provide improved mobile connectivity to support the uptake of new agricultural and business technologies in a cereal cropping and lamb grazing area. Increased mobile coverage will also benefit the operations of the local CFA in responding to natural disasters and vehicle accidents, as well as enabling greater access to essential services for residents. | Complete | Q3, 2023 |
| Telstra Limited | Eastern VIC | Mobile Voice & Data | Alpine, East Gippsland, Wangaratta | VIC | The project will deploy a 42km fibre optic path between the townships of Tambo Crossing and Swifts Creek to create a transmission ‘ring’ between Wangaratta, Bairnsdale and Melbourne, improving the redundancy of the network against service outages. The project will also provide new and improved Telstra mobile coverage at multiple locations along the transmission route, including Mt Hotham, Ensay, Tambo Crossing, Omeo, and Dinner Plain. Upgraded coverage will support business activities and access to services in a number of highly visited tourist locations. | Complete | Q2, 2024 |
| Telstra Limited | Ecklin South | Mobile Voice & Data | Ecklin South | VIC | The project will deploy a new Telstra 4GX macro cell base station in the Corangamite Shire community of Ecklin South. The new base station will provide improved mobile coverage along a transport corridor within the significant dairy region, increasing supply chain efficiency and freight safety. Improved coverage will also support the uptake of new agricultural and business technologies, increased public safety coverage in a high-risk bushfire area, and access to telehealth and education services for the growing community. | Complete | Q3, 2023 |
| Telstra Limited | Euroa North | Mobile Voice & Data | Euroa North | VIC | The project will upgrade the antenna equipment and backhaul capacity at the existing Telstra 3G base station in the Strathbogie Shire locality of Euroa North to provide 4GX mobile coverage. The upgrade will provide improved mobile connectivity to support the uptake of new agricultural and business technologies by local farms, tourism operators and the hospitality sector, as well as development opportunities at the inland rail freight intermodal at Mangalore. Increased mobile coverage will also enable greater access to telehealth, education and other essential services. | Complete | Q4, 2023 |
| Telstra Limited | Fryerstown | Mobile Voice & Data | Fryerstown | VIC | The project will deploy a new Telstra 4GX small cell base station to the Mount Alexander Shire community of Fryerstown. The new base station will provide improved mobile connectivity to support the digital needs of residents, commuters and businesses, as well as the development of new opportunities in goldfields heritage tourism. Increased mobile connectivity will also enable greater access to public safety communications in a high-risk bushfire area. | Complete | Q4, 2023 |
| Telstra Limited | Gazette | Mobile Voice & Data | Gazette | VIC | The project will deploy a Telstra 4G macro cell base station in the Southern Grampians community of Gazette. The new base station will provide new and improved coverage and capacity to support the uptake of new agricultural and business technologies in a grazing region, as well as enabling improved access to essential services including health, education and emergency communications. | Complete | Q3, 2023 |
| Telstra Limited | Gipsy Point | Mobile Voice & Data | Gipsy Point | VIC | The project will deploy a Telstra 4G base station at Gipsy Point, approximately 16km north west of Mallacoota in the East Gippsland Shire. The new base station will increase the resilience and reliability of emergency communications in a bushfire-prone region, as well as supporting local tourism businesses and the delivery of essential services. | Complete | Q3, 2024 |
| Telstra Limited | Halls Gap | Mobile Voice & Data | Halls Gap | VIC | The project will upgrade the capacity of the existing Telstra 4G macro base station in the Northern Grampians town of Halls Gap. The upgrade will provide improved mobile connectivity to support the digital needs of residents, tourists and businesses in a significant tourism, beef and dairy area by enabling the uptake of agricultural and business technologies and the provision of telehealth and education services. | Complete | Q3, 2023 |
| Telstra Limited | Halls Gap East | Mobile Voice & Data | Halls Gap | VIC | The project will deploy a Telstra 4G macro cell base station on the east edge of the town of Halls Gap. The new base station will provide new and improved mobile coverage to a number of tourism and accommodation venues, as well as improving the delivery of essential services including health, education and emergency communications. | Complete | Q2, 2023 |
| Telstra Limited | Kobyboyn | Mobile Voice & Data | Highlands | VIC | The project will deploy a Telstra 4G macro cell base station in the Mitchell Shire community of Kobyboyn. The new base station will provide improved connectivity to support projected residential and business growth in the town due to its proximity to major road and rail transport routes, as well as increased access to essential services including telehealth, education services and emergency communications. | Complete | Q4, 2023 |
| Telstra Limited | Lascelles | Mobile Voice & Data | Lascelles | VIC | The project will deploy a Telstra 4G macro cell base station to the town of Lascelles, located 113km west of Swan Hill in the Yarriambiack shire. The new base station will provide improved mobile connectivity to support the uptake of new agricultural and business technologies for local farms and tourism businesses, as well as improving emergency communications along local highways and increasing access to essential services. | Complete | Q2, 2023 |
| Telstra Limited | Mallee Hwy | Mobile Voice & Data | Galah | VIC | The project will deploy a new Telstra 4GX macro cell base station at Galah on the Mallee Highway near Ouyen. The new base station will provide improved mobile connectivity between Walpeup and Ouyen to support the supply chain along the Highway, which also forms part of a popular touring route. Increased mobile coverage will also enable greater access to essential services for residents in the area, as well as reliable public safety communications in a high-risk grass and bushfire area. | Complete | Q3, 2023 |
| Telstra Limited | Mount Stanley | Mobile Voice & Data | Mount Stanley | VIC | The project will upgrade the antenna equipment and backhaul capacity at the existing Telstra 3G base station at Mount Stanley, which services the Alpine Shire locality of Mudgegonga, to provide 4GX mobile coverage. The upgrade will provide improved mobile connectivity to support the uptake of new agricultural and business technologies by the local agricultural and tourism sectors. Increased mobile coverage will also enable greater access to telehealth, education and public safety communications in a high-risk bushfire area. | Complete | Q4, 2023 |
| Telstra Limited | Nyora | Mobile Voice & Data | Nyora | VIC | The project will deploy a new Telstra 4GX macro cell base station in the South Gippsland community of Nyora. The new base station will provide improved mobile connectivity to support significant anticipated population growth in the district, as well as the operations of retail businesses, industrial and agricultural enterprises, and community facilities which service the growing township. Improved mobile coverage will also enable increased access to telehealth and education opportunities. | Complete | Q3, 2023 |
| Telstra Limited | Rennick | Mobile Voice & Data | Rennick | VIC | The project will upgrade the antenna equipment and backhaul capacity at the existing Telstra 3G base station at Rennick on the border between Victoria and South Australia to provide 4GX mobile coverage. The upgrade will provide improved mobile connectivity along major transport and tourist routes, as well as enabling the uptake of new agricultural and business technologies by the local forestry and agricultural sectors. Increased mobile coverage will also enable improved delivery of emergency services, including cross-border fire and policing services. | Complete | Q1, 2024 |
| Telstra Limited | Scotts Creek | Mobile Voice & Data | Scotts Creek | VIC | The project will deploy a new Telstra 4GX macro cell base station in the Corangamite Shire community of Scotts Creek. The new base station will provide improved mobile connectivity to support the uptake of new agricultural and business technologies in a significant dairy farming and agritourism region. Improved mobile services will also enable increased access to telehealth and education services, as well as public safety coverage in a high-risk bushfire area. | Complete | Q3, 2023 |
| Telstra Limited | Tawonga South | Mobile Voice & Data | Tawonga South | VIC | The project will deploy a new Telstra 4GX macro cell base station at Tawonga South, near Mt Beauty. The new base station will increase mobile coverage and capacity in the area, providing improved mobile connectivity to support the large volume of tourist traffic to the area throughout the year, as well as local primary producers and small businesses. Improved coverage will also support the provision of health and education services. | In Progress | Q1, 2025 |
| Telstra Limited | Toongabbie | Mobile Voice & Data | Toongabbie | VIC | The project will deploy a Telstra 4GX small cell base station to the Latrobe Valley town of Toongabbie. The new base station will provide dedicated mobile coverage to the community, supporting residential growth through improved access to business opportunities and essential services. | Complete | Q3, 2023 |
| Australian Private Networks Pty Ltd (Activ8me) | Jigalong Community Wi-Fi and Telephone Service | Satellite Broadband | Jigalong | WA | The project will deploy a fully managed public satellite Wi-Fi and VoIP telephone solution to the Aboriginal community of Jigalong. The service will provide pay-as-you-go data and voice connectivity to the community, supporting business opportunities in the tourism sector, the operations of the Jigalong Community Incorporated, and access to essential services such as telehealth, education and government services. | Complete | Q2, 2022 |
| Australian Private Networks Pty Ltd (Activ8me) | Kalumburu Community Wi-Fi and Telephone Service | Satellite Broadband | Kalumburu | WA | The project will deploy a fully managed public satellite Wi-Fi and VoIP telephone solution to the Aboriginal community of Kalumburu. The service will provide pay-as-you-go data and voice connectivity to the community, supporting business opportunities in the arts sector, the operations of the Kalumburu Aboriginal Corporation, and access to essential services such as telehealth, education and government services. | Complete | Q4, 2021 |
| CRISP Wireless Pty Ltd | Central Wheatbelt Connectivity Backhaul | Fixed Wireless Broadband | Central Wheatbelt | WA | The project will deploy a fixed wireless network across the Central Wheatbelt region of Western Australia. The network will provide improved connectivity to support the uptake of new agricultural and business technologies by local primary producers and other businesses, as well as enabling improved residential access to essential services such as telehealth and education. | Complete | Q2, 2023 |
| Field Solutions Group Pty Ltd | Regional Australia Network: Wireless Wheatbelt Project - Central Midlands | Fixed Wireless Broadband | Central Midlands | WA | The project will deploy a fixed wireless network in the Dalwallinu, Moora and Wongan-Ballidu Shires within the Central Midlands sub-region of the Western Australian Wheatbelt. The network will provide improved connectivity to support the uptake of new agricultural and business technologies by local primary producers and other businesses, as well as enabling improved residential access to essential services such as telehealth and education. | In Progress | Q2, 2025 |
| NBN Co Limited | Halls Creek Satellite to Fibre to the Premise Technology Change | Fibre Broadband | Halls Creek | WA | This proposal will upgrade the NBN access technology in the town of Halls Creek from Sky Muster satellite to Fibre to the Premises. The upgrade will provide improved broadband connectivity to support the delivery of essential services, such as skills training, education and health services to the town and surrounding areas, as well as supporting business opportunities in tourism, mining and civil construction. | Complete | Q2, 2023 |
| Pivotel Mobile Pty Ltd | Frankland River 4G Network | Mobile Voice & Data | Cranbrook Shire | WA | The project will deploy a Pivotel 4G LTE ‘ecoSphere’ network in the Frankland River region of Western Australia. The network will provide improved broadband and mobile connectivity to support the uptake of new agricultural and business technologies for local primary producers and wine tourism businesses, as well as enabling improved residential access to essential services such as telehealth, education services and emergency communications. | Complete | Q4, 2024 |
| Pivotel Mobile Pty Ltd | South Stirling 4G Network | Mobile Voice & Data | Albany | WA | The project will deploy a Pivotel 4G LTE ‘ecoSphere’ network in the South Stirling region of Western Australia. The network will provide improved broadband and mobile connectivity to support the uptake of new agricultural and business technologies for local primary producers and other businesses, as well as enabling improved residential access to essential services such as telehealth, education services and emergency communications. | Complete | Q4, 2024 |
| Telstra Limited | Ardyaloon | Mobile Voice & Data | Dampier Peninsula | WA | The project will upgrade the capacity of the existing Telstra 4G macro cell base station in the Ardyaloon (One Arm Point) community north east of Broome. The upgrade will provide improved mobile connectivity to the community to support tourism and business growth, as well as access to telehealth, education and other essential services. | Complete | Q3, 2024 |
| Telstra Limited | Arthur River North | Mobile Voice & Data | Williams | WA | The project will deploy a new Telstra 4GX macro cell base station to the north of the Wheatbelt community of Arthur River. The new base station will provide improved mobile connectivity to support the uptake of new agricultural and business technologies in an agricultural area. Increased mobile coverage will also enable greater access to essential services, as well as improved public safety communications along a portion of the Albany Highway. | In Progress | Q2, 2025 |
| Telstra Limited | Balbarrup | Mobile Voice & Data | Balbarrup | WA | The project will deploy a new Telstra 4GX macro cell base station to the Balbarrup locality near Manjimup. The new base station will provide improved mobile connectivity to support the uptake of agricultural and business technologies in an expanding horticultural region. Increased mobile coverage will also enable improved public safety communications in a high-risk bushfire area and along major regional transport routes, as well as better access to education and other essential services. | In Progress | Q1, 2025 |
| Telstra Limited | Bayulu | Mobile Voice & Data | St George Ranges | WA | The project will deploy a new Telstra 4GX small cell base station in the Aboriginal community of Bayulu, south of Fitzroy Crossing. The new base station will provide improved mobile connectivity to support the operations of local community facilities, including the Community Store, Hall and Women's Centre. Increased mobile coverage will also enable greater access to telehealth, education and other essential services. | In Progress | Q2, 2025 |
| Telstra Limited | Bidyadanga | Mobile Voice & Data | Lagrange | WA | The project will upgrade the capacity of the existing Telstra 4G base station in the Bidyadanga Aboriginal community. The upgrade will provide improved mobile connectivity to support growth opportunities in small business and tourism, as well as enabling increased residential access to essential services such as telehealth, education services and government services. | Complete | Q1, 2024 |
| Telstra Limited | Caiguna | Mobile Voice & Data | Caiguna | WA | The project will upgrade antenna equipment and backhaul capacity at the existing Telstra 3G base station in the small roadhouse community of Caiguna to provide Telstra 4GX and Internet of Things coverage to the area and along the Eyre Highway. The upgrade will provide improved connectivity to support the delivery of tourism, accommodation, hospitality and retail services at the roadhouse. | Complete | Q3, 2024 |
| Telstra Limited | Carbunup | Mobile Voice & Data | Metricup | WA | The project will upgrade the capacity of the existing Telstra 4G macro cell base station at Carbunup River, near Busselton. The upgrade will provide improved mobile connectivity to support the digital needs of residents and local small businesses, including tourist retreats, retail, horse boarding and riding facilities and vineyards. Improved connectivity will also provide increased public safety coverage along the Bussell Highway and in a high-risk bushfire region. | Complete | Q1, 2023 |
| Telstra Limited | Cave Point Lighthouse | Mobile Voice & Data | Torndirrup | WA | The project will deploy a Telstra 4G macro cell base station on the Cave Point Lighthouse, a popular tourist attraction within the Torndirrup National Park with limited mobile coverage. The new base station will provide improved mobile coverage to support the safety and amenity of visitors at the site and surrounding National Park, particularly through increased access to emergency communications. | In Progress | Q2, 2025 |
| Telstra Limited | Cocklebiddy | Mobile Voice & Data | Cocklebiddy | WA | The project will upgrade antenna equipment and backhaul capacity at the existing Telstra 3G base station in the small roadhouse community of Cocklebiddy to provide Telstra 4GX and Internet of Things coverage to the area and along the Eyre Highway. The upgrade will provide improved connectivity to support the delivery of tourism, accommodation, hospitality and retail services at the roadhouse. | Complete | Q3, 2024 |
| Telstra Limited | Condingup | Mobile Voice & Data | Condingup | WA | The project will upgrade the coverage and capacity at the existing Telstra 4G macro cell base station at Condingup. The new base station will address a coverage gap outside of the main township and will provide improved connectivity to support the operations of local businesses and community facilities, as well as enabling increased residential access to essential services. | Complete | Q4, 2024 |
| Telstra Limited | Coolup West | Mobile Voice & Data | Waroona | WA | The project will deploy a new Telstra 4GX macro cell base station to the Murray Shire community of Coolup West. The new base station will provide improved mobile connectivity to support increased residential growth in the area, as well as the uptake of agricultural and business technologies by farms and tourism enterprises. Increased mobile coverage will also enable greater access to public safety communications in a high-risk bushfire area. | In Progress | Q2, 2025 |
| Telstra Limited | Coral Bay | Mobile Voice & Data | Coral Bay | WA | The project will upgrade the capacity of the existing Telstra 4G macro cell base station at the holiday resort town of Coral Bay. The upgrade will provide improved mobile connectivity to support the expected growth of the local tourism industry, as well as enabling increased residential access to essential services such as telehealth and education services. | Complete | Q2, 2024 |
| Telstra Limited | Cygnet Bay | Mobile Voice & Data | Cygnet Bay | WA | The project will deploy a Telstra 4G small cell base station at Cygnet Bay, a popular tourist location on the Dampier Peninsula. The new cell will provide improved mobile connectivity to support the operations of local pearling, marine research and tourism organisations, as well as enabling increased residential access to essential services such as telehealth, education and government services. | In Progress | Q2, 2025 |
| Telstra Limited | Fitzroy Crossing | Mobile Voice & Data | Fitzroy Crossing | WA | The project will upgrade the capacity of the existing Telstra 4G macro cell base station in the Kimberley town of Fitzroy Crossing. The upgrade will provide improved mobile connectivity to support business opportunities in tourism and the arts, as well as enabling greater access to telehealth, education and other essential services. | Complete | Q2, 2024 |
| Telstra Limited | Geraldton | Mobile Voice & Data | Moonyoonooka | WA | The project will deploy a new Telstra 4GX small cell base station to the Moonyoonooka area to the east of Geraldton. The new base station will provide improved mobile connectivity to support the operations of a number of businesses, including local retail, recreation facilities and horticultural farms. Increased connectivity will also enable greater access to essential services for residents and employees in the area. | Complete | Q3, 2023 |
| Telstra Limited | Greenbushes-Boyup | Mobile Voice & Data | Catterick | WA | The project will deploy a Telstra 4G macro cell base station in the Catterick locality near Greenbushes in Western Australia. The new base station will provide improved mobile coverage to support the uptake of agricultural and business technologies by primary producers and other local industries, as well as enabling increased residential and commuter access to essential services and emergency communications along two major sub-regional roads. | Complete | Q4, 2024 |
| Telstra Limited | Joy Springs | Mobile Voice & Data | St George Ranges | WA | The project will deploy a new Telstra 4GX small cell base station in the Aboriginal community of Joy Springs, east of Fitzroy Crossing. The new base station will provide improved mobile connectivity to support the digital needs of residents and businesses, including a number of community facilities. Increased mobile coverage will also enable greater access to telehealth, education and other essential services. | In Progress | Q2, 2025 |
| Telstra Limited | Koongie Park | Mobile Voice & Data | Mueller Ranges | WA | The project will deploy a new Telstra 4GX small cell base station in the Aboriginal community of Koongie Park (Lamboo Gunian) near Halls Creek. The new base station will provide improved mobile connectivity to support expanded community services at the Administration Centre and the development of local education facilities. Increased mobile coverage will also enable greater access to essential services, including telehealth. | In Progress | Q1, 2025 |
| Telstra Limited | Koorabye | Mobile Voice & Data | St George Ranges | WA | The project will deploy a new Telstra 4GX small cell base station in the Aboriginal community of Koorabye. The new base station will provide improved mobile connectivity to support the development of the local tourism industry, as well as the local operations of WA and Commonwealth agencies. Increased mobile coverage will also enable greater access to telehealth, education and other essential services. | In Progress | Q2, 2025 |
| Telstra Limited | Kununurra South | Mobile Voice & Data | Kununurra | WA | The project will deploy a new Telstra 4GX macro cell base station in the town of Crossing Falls, south of Kununurra. The new base station will provide improved mobile connectivity to the expanding township, as well as to the nearby Aboriginal community at Mud Springs, enabling greater access to essential services and increasing public safety coverage for local fire services. | In Progress | Q1, 2025 |
| Telstra Limited | Learmonth | Mobile Voice & Data | Learmonth | WA | The project will deploy a new Telstra 4GX macro cell base station at Learmonth Airport near Exmouth. The new base station will provide improved mobile connectivity to support expanded business operations and increased passenger traffic at the airport from tourists, fly-in fly-out workers and other travellers. There are also potential applications for increased mobile connectivity at the nearby solar observatory. | Complete | Q3, 2024 |
| Telstra Limited | Meekatharra | Mobile Voice & Data | Meekatharra | WA | The project will upgrade the capacity of the existing Telstra 4G macro cell base station in the Mid-West WA community of Meekatharra. The upgrade will provide improved mobile connectivity to support increased demand on the mobile network from regional resource projects and agricultural industries, as well as the operations of local businesses in the community and at the nearby Meekatharra Airport. Increased connectivity will also enable greater access to telehealth, education and other essential services. | Complete | Q4, 2023 |
| Telstra Limited | Mowanjum | Mobile Voice & Data | Derby | WA | The project will deploy a new Telstra 4GX small cell base station in the Aboriginal community of Mowanjum, south east of Derby. The new base station will provide improved mobile connectivity to support the operations of local community facilities, as well as the expansion of opportunities in the art tourism sector. Increased mobile coverage will also enable greater access to telehealth, education and other essential services. | Complete | Q1, 2025 |
| Telstra Limited | Napier North | Mobile Voice & Data | Narrikup | WA | The project will deploy a new Telstra 4GX macro cell base station to the north of the town of Napier. The new base station will provide improved mobile connectivity to support the uptake of agricultural and business technologies in a farming area with limited existing coverage. Increased connectivity will also enable greater access to essential services, as well as public safety coverage in a high-risk bushfire area. | In Progress | Q1, 2025 |
| Telstra Limited | Oakes | Mobile Voice & Data | Arrowsmith | WA | The project will deploy a new Telstra 4GX macro cell base station at Oakes along the Brand Highway. The new base station will provide improved mobile connectivity along a major transport corridor between Perth and Geraldton, increasing amenity, safety and efficiency for freight providers and commuters. | Complete | Q3, 2023 |
| Telstra Limited | Ord North | Mobile Voice & Data | Kununurra | WA | The project will deploy a new Telstra 4GX macro cell base station to the north of Kununurra. The new base station will provide improved mobile connectivity to support the uptake of new agricultural and business technologies in an area with tropical fruit farms, tourism businesses and other industries. Increased connectivity will also enable greater access to essential services for the residential satellite suburbs outside of Kununurra. | Complete | Q2, 2025 |
| Telstra Limited | Pandanus Park | Mobile Voice & Data | Willare | WA | The project will deploy a new Telstra 4GX small cell base station in the Aboriginal community of Pandanus Park, near Derby. The new base station will provide improved mobile connectivity to support the development of business opportunities in sandmining, aquaculture, cultural tourism, maintenance and retail, as well as the operations of local community facilities. Increased mobile connectivity will also enable greater access to telehealth, education and other essential services. | In Progress | Q2, 2025 |
| Telstra Limited | Takalarup | Mobile Voice & Data | Takalarup | WA | The project will deploy a new Telstra 4GX macro cell base station in the Great Southern community of Takalarup. The new base station will provide improved mobile connectivity to support the uptake of agricultural and business technologies in a grain growing region. Increased connectivity will also enable greater access to telehealth, education and other essential services, as well as on-farm safety coverage. | Complete | Q1, 2023 |
| Telstra Limited | Warradarge | Mobile Voice & Data | Warradarge | WA | The project will deploy a new Telstra 4GX macro cell base station at Warradarge along the Brand Highway. The new base station will provide improved mobile connectivity to support the operations of local industries, including the Warradarge Wind Farm, the local Roadhouse and a number of agricultural properties. Increased coverage will also enable greater commuter amenity and public safety along part of the Brand Highway, as well as improved emergency telecommunications in a fire risk area. | In Progress | Q2, 2025 |
| Telstra Limited | Yiyili | Mobile Voice & Data | Mueller Ranges | WA | The project will deploy a new Telstra 4GX small cell base station in the Aboriginal community of Yiyili. The new base station will provide improved mobile connectivity to support the digital needs of residents and community facilities in the area, including the local school, police and health services. Increased mobile coverage will also enable greater access to other essential services. | In Progress | Q2, 2025 |

## Table 2: Regional Connectivity Program Round 2 Project Status

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Grantee | Project Name | Technology Type | Location | State | Project Description | RCP Project Status | Actual / Expected Project Completion Date |
| Telstra Limited | Christmas Island | Mobile Voice & Data | Christmas Island | External Territory of Australia | The project will upgrade four Telstra 2G macro cell base stations to 4GX macro cell base stations at Christmas Island and deploy one new Telstra 4GX macro cell base stations at Christmas Island’s airport. | In Progress | Q2, 2025 |
| Ace Internet Services Pty Ltd | Southern Highlands Network Upgrade - Bullio | Fixed Wireless Broadband | Bullio | NSW | The project will upgrade the fixed wireless network in the Bullio area of the Southern Highlands, maximising the existing network and ensuring greater reliability and capacity. | Complete | Q2, 2023 |
| Ace Internet Services Pty Ltd | Southern Highlands Network Upgrade - Tugalong Road | Fixed Wireless Broadband | Canyonleigh | NSW | The project will upgrade the fixed wireless network and its corresponding backhaul along Tugalong Road in the Canyonleigh area of the Southern Highlands, maximising the existing network and ensuring greater reliability and capacity. | Complete | Q2, 2023 |
| Pivotel Mobile Pty Ltd | Dubbo – Digital Connectivity Network | Mobile Voice & Data | Dubbo | NSW | The project will build a 4G ecoSphere network, as well as an mmWave Fixed Wireless Access network in the north-west of Dubbo, providing coverage to the regional towns of Rawsonville, Dickygundi, Minore and Terramungamine. | Removed | - |
| Telstra Limited | Boggabilla | Mobile Voice & Data | Boggabilla | NSW | The project will deploy one new Telstra small cell mobile site, providing improved handheld coverage to the Boggabilla area. | Complete | Q3, 2024 |
| Telstra Limited | Bulga | Mobile Voice & Data | Bulga | NSW | The project will deploy a new Telstra macro cell mobile site, providing improved connectivity to the Bulga area. | In Progress | Q2, 2025 |
| Telstra Limited | Burrendong Way | Mobile Voice & Data | Mullion Creek, Euchareena | NSW | The project will deploy two new Telstra macro mobile sites and one new Telstra small cell site to provide new and improved handheld coverage along sections of Burrendong Way, as well as dedicated coverage for Mullion Creek. | In Progress | Q2, 2025 |
| Telstra Limited | Henty Field Days | Mobile Voice & Data | Henty | NSW | The project will deploy one new Telstra macro cell mobile site, providing improved handheld coverage to site of the Henty Machinery Field Days and surrounding areas. | Complete | Q3, 2023 |
| Telstra Limited | Mt Tomah | Mobile Voice & Data | Mt Tomah | NSW | The project will deploy a new Telstra macro mobile site, providing improved coverage to the town of Mt Tomah and along a nearby section of the Bells Line Road. | In Progress | Q2, 2025 |
| Telstra Limited | Nanima Village | Mobile Voice & Data | Nanima Village | NSW | The project will deploy a new Telstra small cell mobile site, providing improved handheld coverage to Nanima Village, an Aboriginal community in the Western Plains Regional area of NSW. | In Progress | Q2, 2025 |
| Telstra Limited | Princes Highway - Ulladulla to Batemans Bay | Mobile Voice & Data | Termeil, Cullendulla | NSW | The project will deploy two new Telstra macro mobile sites, one in Termeil and one in Cullendulla, providing improved coverage to sections of the Princes Highway between Ulladulla and Batemans Bay. | In Progress | Q2, 2025 |
| Telstra Limited | Quaama | Mobile Voice & Data | Quaama | NSW | The project will deploy one new Telstra small cell mobile site, providing improved handheld coverage to the Quaama town and surrounding area. | Complete | Q2, 2024 |
| Telstra Limited | Quandialla | Mobile Voice & Data | Quandialla | NSW | The project will deploy a new Telstra small cell mobile site, providing improved handheld coverage to the Quandialla area. | Complete | Q3, 2023 |
| Telstra Limited | Silver City Highway | Mobile Voice & Data | Anabranch, Wentworth | NSW | The project will deploy three new Telstra macro mobile sites, providing new and improved handheld coverage along the Silver City Highway in the Anabranch and Wentworth areas. | In Progress | Q1, 2025 |
| Telstra Limited | Upper Horton | Mobile Voice & Data | Upper Horton | NSW | The project will deploy a new Telstra small cell mobile site, providing improved handheld coverage to the town of Upper Horton. | In Progress | Q1, 2025 |
| BizCom NT Pty Ltd | Fibre to the Home (White Gums) | Fibre Broadband | White Gums | NT | The project will deliver a fibre broadband network to the suburb of White Gums in Alice Springs, providing improved connectivity to the area. | Complete | Q4, 2024 |
| Telstra Limited | Acacia Hills | Mobile Voice & Data | Acacia Hills | NT | The project will deploy one new Telstra macro cell mobile base station to service the rural locality of Acacia Hills. | In Progress | Q1, 2025 |
| Telstra Limited | Alyangula | Mobile Voice & Data | Alyangula | NT | The project will deploy a new Telstra macro mobile base station in the Alyangula township to provide improved handheld coverage. | Complete | Q2, 2023 |
| Telstra Limited | Angurugu | Mobile Voice & Data | Angurugu | NT | The project will deploy a new Telstra small cell mobile base station to service the Aboriginal community of Angurugu, situated on the island of Groote Eylandt. | In Progress | Q2, 2025 |
| Telstra Limited | Douglas Daly | Mobile Voice & Data | Douglas Daly | NT | The project will deploy one new Telstra macro cell base station in the Douglas-Daly region, providing new and improved coverage to the area. | In Progress | Q2, 2025 |
| Telstra Limited | Edith River | Mobile Voice & Data | Edith River | NT | The project will deploy a new Telstra macro cell mobile site to provide new and improved connectivity to the Edith locality, located along the Stuart Highway. | In Progress | Q2, 2025 |
| Telstra Limited | Gemtree | Mobile Voice & Data | Gemtree | NT | The project will deploy a new Telstra macro mobile site, providing new and improved handheld coverage to Gemtree, located in Anmatjere. | Complete | Q4, 2024 |
| Telstra Limited | Middle Point | Mobile Voice & Data | Middle Point | NT | The project will deploy a new Telstra macro mobile base station to service the rural locality of Middle Point and a section of the Arnhem Highway. | Complete | Q3, 2024 |
| Telstra Limited | Milyakburra Island | Mobile Voice & Data | Milyakburra Island | NT | The project will deploy a new Telstra macro cell mobile site at the Aboriginal community at Milyakburra Island, providing improved coverage to the area. | In Progress | Q2, 2025 |
| Connected Farms Pty Ltd | Livingstone Agricultural Precinct | Fixed Wireless Broadband | Livingstone | QLD | The project will deploy a fixed wireless network providing broadband coverage to the Livingstone agricultural precinct and neighbouring areas. The network will extend mobile and broadband connectivity and voice over LTE in the area. | Complete | Q3, 2024 |
| Field Solutions Group (FSG) | Regional Australia Network: Mareeba Cairns Road | Fixed Wireless Broadband | Mareeba | QLD | The project is an extension of a Round 1 RCP project and will deploy a fixed wireless network across the Mareeba local government area. | Removed | - |
| NBN Co Limited | Boulia QLD - nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) | Fibre Broadband | Boulia | QLD | The project will upgrade the nbn™ service technology in the town of Boulia from nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises. | Complete | Q2, 2024 |
| NBN Co Limited | Cunnamulla QLD - nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) | Fibre Broadband | Cunnamulla | QLD | The project will upgrade the nbn™ service technology in the town of Cunnamulla from nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) technology. | Complete | Q2, 2024 |
| NBN Co Limited | Julia Creek QLD - nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) | Fibre Broadband | Julia Creek | QLD | The project will upgrade the nbn™ service technology in the town of Julia Creek from nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises. | Complete | Q3, 2024 |
| NBN Co Limited | Quilpie QLD - nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) Technology Switch | Fibre Broadband | Quilpie | QLD | The project will upgrade the nbn™ service technology in the town of Quilpie from nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) technology. | Complete | Q2, 2024 |
| Queensland Capacity Network Pty Ltd | Mackay Regional Project - Finch Hatton, Pinnacle, Eungella, Marian, Mirani, Gargett | Fixed Wireless Broadband | Mackay | QLD | The project will deploy a fixed wireless network and corresponding fibre backhaul in the Mackay area, including Finch Hatton, Pinnacle, Gargett, Eungella and the surrounding areas of Marian and Mirani. | Removed | - |
| Telstra Limited | Bollon | Mobile Voice & Data | Bollon | QLD | The project will upgrade the Telstra macro cell mobile site, providing improved handheld coverage to the Bollon area. | Complete | Q1, 2024 |
| Telstra Limited | Burketown to Normanton Fibre | Fibre Backhaul | Burketown and Normanton | QLD | The project will deploy 226 km of fibre optic cable between Burketown and Normanton, North-West Queensland, and supporting infrastructure to complete a fibre loop encircling North-West Queensland. This will create additional network redundancy for 66 per cent of Queensland and additional network resiliency for 780,000 Queenslanders across 15 Local Government Areas. | Complete | Q4, 2024 |
| Telstra Limited | Cherbourg | Mobile Voice & Data | Cherbourg | QLD | This project will deploy a new Telstra macro mobile site, providing new and improved handheld coverage to the Cherbourg township and the surrounding area. | Complete | Q4, 2024 |
| Telstra Limited | Cooktown West | Mobile Voice & Data | Cooktown | QLD | The project will deploy a new Telstra macro cell mobile site, providing improved handheld coverage to the Cooktown township, including the Cooktown Airport. | In Progress | Q1, 2025 |
| Telstra Limited | Doomadgee | Mobile Voice & Data | Doomadgee | QLD | The project will deploy a new Telstra macro cell base station to provide new coverage to the Aboriginal township of Doomadgee. | Complete | Q3, 2024 |
| Telstra Limited | Forrest Beach | Mobile Voice & Data | Forrest Beach | QLD | The project will deploy a new Telstra macro cell mobile site, providing new and improved handheld coverage to Forrest Beach, the township, Allingham and the wider surrounding area. | Complete | Q4, 2024 |
| Telstra Limited | Inskip Point | Mobile Voice & Data | Inskip Point | QLD | The project will deploy a new Telstra small cell mobile site providing coverage to Inskip Point and the southern coastline of Fraser Island. | In Progress | Q2, 2025 |
| Telstra Limited | Lockhart River | Mobile Voice & Data | Lockhart River | QLD | The project will upgrade the Telstra macro cell base station and transmission infrastructure in the remote Aboriginal community of Lockhart River, providing improved mobile coverage to the area. | Complete | Q4, 2023 |
| Telstra Limited | Pasha | Mobile Voice & Data | Pasha | QLD | The project will upgrade one Telstra macro cell mobile station at Pasha to provide improved handheld coverage to the Pasha area and bordering highway. | Complete | Q2, 2024 |
| Telstra Limited | Ravenswood | Mobile Voice & Data | Ravenswood | QLD | The project will deploy a new Telstra macro mobile site, providing improved handheld coverage to the Ravenswood township. | Complete | Q2, 2024 |
| Telstra Limited | Seisia | Mobile Voice & Data | Seisia, New Mapoon | QLD | The project will deploy one new Telstra macro cell base station at Seisia and will provide new coverage in Seisia, New Mapoon and surrounding area. | In Progress | Q2, 2025 |
| Telstra Limited | Woorabinda | Mobile Voice & Data | Woorabinda | QLD | The project will deploy one new Telstra macro base station in the Aboriginal community of Woorabinda, delivering new and improved coverage to the area. | Complete | Q3, 2024 |
| Wi-Sky Queensland Pty Ltd | Wi-Sky Qld Far North Queensland Connectivity Project - Gulf Development Road | Fixed Wireless Broadband | Gulf Development Road | QLD | The project will deploy a high-speed fixed wireless broadband network, backhaul, public Wi-Fi and free LoRaWAN network to 20,000km2 of Far Northern Western Queensland. The project will improve the connectivity in the area from Normanton to Georgetown and the Gilbert River Agricultural Precinct. | Complete | Q3, 2024 |
| Wi-Sky Queensland Pty Ltd | Wi-Sky Qld Far North Queensland Connectivity Project - Richmond Croydon Road | Fixed Wireless Broadband | Richmond Croydon Road | QLD | The project will deploy a high-speed fixed wireless broadband network, backhaul, public Wi-Fi and free LoRaWAN network to 20,000km2 of Far North Western Queensland. The project will improve connectivity in the area between Richmond and the town of Croydon and surrounding area. | Complete | Q3, 2024 |
| NBN Co Limited | Lameroo and Pinnaroo SA – nbn™ Sky Muster™ Satellite to nbn™ Fixed Wireless Technology Switch | Fixed Wireless Broadband | Pinnaroo, Lameroo, Peake | SA | The project will upgrade the nbn™ service technology in the towns of Lameroo and Pinnaroo from nbn™ Sky Muster Satellite to nbn™ Fixed Wireless technology. | Complete | Q3, 2024 |
| Telstra Limited | Ceduna South | Mobile Voice & Data | Ceduna Waters | SA | The project will deploy a new Telstra macro mobile site, providing improved coverage to Ceduna South and the surrounding area. | In Progress | Q2, 2025 |
| Telstra Limited | Greenways | Mobile Voice & Data | Greenways | SA | The project will deploy a new Telstra macro cell mobile site, providing new and improved handheld coverage to the Greenways area. | Complete | Q3, 2024 |
| Telstra Limited | Gum Creek | Mobile Voice & Data | Gum Creek | SA | The project will deploy a new Telstra macro cell mobile site, providing new and improved handheld coverage to the Gum Creek area. | Complete | Q4, 2024 |
| Telstra Limited | Mallee - Lowan | Mobile Voice & Data | Bowhill | SA | The project will deploy a new Telstra macro mobile site in Mallee providing improved coverage to the farming areas surrounding the Lowan Conservation Park, Bowhill and Younghusband and sections of the Mallee Highway. | In Progress | Q1, 2025 |
| Telstra Limited | Oakden | Mobile Voice & Data | Oakden Hills | SA | The project will upgrade the Telstra macro cell mobile site to provide improved handheld coverage to the Oakden area. | Complete | Q2, 2024 |
| Telstra Limited | Parilla | Mobile Voice & Data | Parilla | SA | The project will deploy a new Telstra macro cell mobile site, providing improved handheld coverage to the Parilla area. | Complete | Q3, 2024 |
| Telstra Limited | Pekina | Mobile Voice & Data | Pekina | SA | The project will deploy a new Telstra macro mobile site, providing improved coverage to Pekina and the Orroroo and Carrieton LGAs. | Complete | Q3, 2024 |
| Telstra Limited | Vivonne Bay | Mobile Voice & Data | Vivonne Bay | SA | The project will upgrade a Telstra macro mobile site in Vivonne Bay on Kangaroo Island, providing improved coverage to the area. | Complete | Q3, 2024 |
| Telstra Limited | Wattle Range - Short | Mobile Voice & Data | Short | SA | The project will deploy a new Telstra macro mobile site in Short near Wattle Range, providing improved handheld coverage to the area. | In Progress | Q2, 2025 |
| Telstra Limited | Wirrulla Hill | Mobile Voice & Data | Wirrulla | SA | The project will upgrade a Telstra macro mobile site in Wirrulla Hill providing improved coverage to the area or Wirrulla and a stretch of the Eyre Highway. | Complete | Q2, 2024 |
| Connected Farms Pty Ltd | Cradle Coast Agricultural Precinct | Fixed Wireless Broadband | Cradle Coast | TAS | The project will deploy a place-based wide area fixed wireless network providing broadband coverage to the Cradle Coast agricultural precinct and neighbouring areas. The network will extend broadband connectivity and voice over LTE in the area. | Complete | Q3, 2024 |
| Telstra Limited | North West Coast Tasmania | Mobile Voice & Data | Redpa, Boat Harbour, Port Latta, Scotchtown | TAS | The project will deploy four new Telstra macro mobile sites at Boat Harbour, Port Latta, Marrawah/Redpa and Lower Scotchtown, providing improved coverage across the North West Coast of Tasmania. | Complete | Q3, 2024 |
| Telstra Limited | Northern Midlands | Mobile Voice & Data | Deddington, Royal George, Lake Leake | TAS | The project will deploy three new Telstra macro mobile sites at Deddington, Royal George and Lake Leake, providing new and improved coverage to the area. | In Progress | Q2, 2025 |
| Telstra Limited | Pelham | Mobile Voice & Data | Pelham | TAS | The project will deploy a new Telstra macro mobile site, providing improved coverage to Pelham in the Central Highlands and along the Lyell Highway. | Complete | Q2, 2024 |
| NBN Co Limited | Sea Lake nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) Technology Switch | Fibre Broadband | Sea Lake | VIC | The project will upgrade the nbn™ service technology in the town of Sea Lake from nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) technology | Complete | Q2, 2024 |
| Pivotel Mobile Pty Ltd | Wimmera Southern Mallee – Digital Connectivity Network | Mobile Voice & Data | Southern Mallee | VIC | The project will build a 4G ecoSphere network, as well as an mmWave Fixed Wireless Access network in the Wimmera Southern Mallee (WSM) region of Western Victoria. | Removed | - |
| Telstra Limited | Bairnsdale Aerodrome | Mobile Voice & Data | Bairnsdale | VIC | The project will deploy a new high-capacity Telstra macro mobile site in at the Bairnsdale Aerodrome. This will result in new and improved coverage to the Aerodrome, Bairnsdale, the Great Alpine Road and the Princes Highway | In Progress | Q1, 2025 |
| Telstra Limited | Boho South | Mobile Voice & Data | Boho South | VIC | This project will deploy a new Telstra macro mobile site with new transmission backhaul to the locality of Boho South, providing improved mobile coverage to the area. | Complete | Q4, 2024 |
| Telstra Limited | East Bendigo | Mobile Voice & Data | Axedale, Goornong, Colbinabbin, Toolleen | VIC | The project will deploy seven new macro mobiles sites and fibre backhaul to the east of Bendigo, at Fosterville Mine, Axedale, Goornong, Knowsley, Colbinabbin, Toolleen Sports Club, Heathcote Raceway, providing improved handheld coverage to the area. | In Progress | Q2, 2025 |
| Telstra Limited | Goorambat | Mobile Voice & Data | Goorambat | VIC | The project will deploy a new Telstra macro mobile site at Goorambat in northern Victoria, providing improved handheld coverage to the area. | Complete | Q1, 2025 |
| Telstra Limited | Lindenow Food Bowl | Mobile Voice & Data | Calulu and Woodglen | VIC | The project will deploy two new Telstra macro mobile sites at Calulu and Woodglen. These locations are in the Lindenow Valley, forming part of the Lindenow Food Bowl. | In Progress | Q2, 2025 |
| Telstra Limited | Maroona | Mobile Voice & Data | Maroona | VIC | The project will deploy a new Telstra macro mobile site, providing new and improved handheld coverage to Maroona and surrounding area. | Complete | Q4, 2024 |
| Telstra Limited | Nicholson | Mobile Voice & Data | Nicholson | VIC | The project will deploy a new high-capacity Telstra macro mobile site to the Nicholson area. This will result in new and improved coverage to the Great Alpine Road, and the Princes Highway. | Complete | Q4, 2024 |
| Telstra Limited | Noojee | Mobile Voice & Data | Noojee | VIC | The project will deploy a new Telstra macro mobile site, providing improved coverage to Noojee in the Gippsland region. | In Progress | Q2, 2025 |
| Telstra Limited | Noorat | Mobile Voice & Data | Noorat | VIC | The project will deploy a new Telstra macro cell mobile site, providing improved handheld coverage to the Noorat area. | In Progress | Q2, 2025 |
| Telstra Limited | Orford | Mobile Voice & Data | Orford | VIC | This project will deploy a new macro cell site and required fibre backhaul in Orford. This solution will provide new and improved coverage to the Orford area and along the Princes Highway. | Complete | Q2, 2024 |
| Telstra Limited | Tarrawingee | Mobile Voice & Data | Tarrawingee | VIC | The project will deploy a new Telstra macro cell mobile site, providing improved handheld coverage to the Tarrawingee area. | Complete | Q4, 2024 |
| Telstra Limited | Tylden | Mobile Voice & Data | Tylden | VIC | This project will deploy a new macro cell site and required fibre backhaul in Tylden. This solution will provide new and improved coverage along the Kyneton to Trentham roadway, along the Calder Highway, and along the nearby rail line. | Complete | Q4, 2024 |
| Telstra Limited | Walkerville | Mobile Voice & Data | Walkerville | VIC | The project will deploy a new Telstra macro cell mobile site, providing improved handheld coverage to the Walkerville area. | Complete | Q4, 2024 |
| Australian Private Networks Pty Ltd (Activ8me) | Kalumburu Outstations Connectivity | Satellite Broadband | Kalumburu | WA | The project will deploy a fully managed public satellite Wi-Fi and Voice over Internet Protocol (VoIP) telephone solution to the Aboriginal community of the Kalumburu Outstations. | Complete | Q3, 2024 |
| Australian Private Networks Pty Ltd (Activ8me) | Mowanjum Community Wi-Fi and Telephone Service | Satellite Broadband | Mowanjum | WA | The project will deploy a fully managed public satellite Wi-Fi and Voice over Internet Protocol (VoIP) telephone solution to the Aboriginal community of Mowanjum. | Complete | Q1, 2023 |
| Australian Private Networks Pty Ltd (Activ8me) | Tjuntjuntjara Community Wi-Fi and Telephone Service | Satellite Broadband | Tjuntjuntjara | WA | This project will deploy an upgraded Broadband Wi-Fi Internet and Voice over Internet Protocol (VoIP) Telephone services to the Tjuntjuntjara Aboriginal Community. | Complete | Q4, 2023 |
| CipherTel Pty Ltd | Western Desert Aboriginal Lands Communications Network | Fixed Wireless Broadband | Western Desert Aboriginal Lands | WA | The project will install the Western Desert Aboriginal Lands Communication Network, a broadband communications system, to service the remote Aboriginal communities of Kunawarritji, Punmu, Parnngurr and Jigalong. | In Progress | Q2, 2025 |
| CRISP Wireless Pty Ltd | Central Wheatbelt Connectivity Backhaul Expansion | Fixed Wireless Broadband | Central Wheatbelt | WA | The project is an extension of a Round 1 RCP project and will deploy a fixed wireless broadband network, comprising 11 repeater stations across 6 local government areas, to connect the existing CRISP wireless network to the Central, Eastern and Southern parts of the Central Wheatbelt region. | Complete | Q4, 2023 |
| NBN Co Limited | Fitzroy Crossing WA - nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) Technology Switch | Fibre Broadband | Fitzroy Crossing | WA | The project will upgrade the nbn™ service technology in the town of Fitzroy Crossing from nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises. | Removed | - |
| NBN Co Limited | Mullewa WA- nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) Technology Switch | Fibre Broadband | Mullewa | WA | The project will upgrade the nbn™ service technology in the town of Mullewa from nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) technology. | Complete | Q2, 2024 |
| NBN Co Limited | Onslow WA – nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) Technology Switch | Fibre Broadband | Onslow | WA | The project will upgrade the nbn™ service technology in the town of Onslow from nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises. | Complete | Q2, 2024 |
| NBN Co Limited | Ravensthorpe WA - nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) Technology Switch | Fibre Broadband | Ravensthorpe | WA | The project will upgrade the nbn™ service technology in the town of Ravensthorpe from nbn™ Sky Muster Satellite to nbn™ Fibre to the Premises (FTTP) technology. | Complete | Q2, 2024 |
| Optus | Satellite Femto Cell Greenfields Western Australia | Mobile Voice & Data | Western Australia | WA | The project will deploy nine new satellite femto cells in Western Australia to provide improved mobile coverage at nine popular and remote surf beaches along the West Australian coast identified as a risk of shark attacks. | Removed | - |
| Orro Pty Ltd | Radio Access Network: Shire of Halls Creek | Fixed Wireless Broadband | Halls Creek | WA | The project will construct a fixed wireless network to deliver reliable, high speed broadband services and public Wi-Fi to the remote Aboriginal communities of Balgo (Wirrimanu), Billiluna (Mindibungu), Mulan and Ringer Soak (Kundat Djaru) located in the Shire of Halls Creek in the East Kimberley region of Western Australia. | Removed | - |
| Swoop (NodeOne) | Broadband Improvement in the Busselton Region | Fixed Wireless Broadband | Busselton | WA | The project will deploy four new fixed wireless sites and corresponding microwave and fibre backhaul to improve broadband services in the Busselton region of Western Australia. | Complete | Q2, 2024 |
| Swoop (NodeOne) | Broadband Improvement in the Harvey Agriculture Region | Fixed Wireless Broadband | Harvey | WA | The project will upgrade two sites and deploy six new fixed wireless sites to improve broadband services in the Harvey region of Western Australia. | Complete | Q1, 2025 |
| Telstra Limited | Coconut Wells | Mobile Voice & Data | Coconut Wells | WA | The project will deploy a new Telstra small cell mobile site to deliver new and improved handheld coverage to the Goolarabooloo Millibinyarri (Coconut Wells) Community. | In Progress | Q2, 2025 |
| Telstra Limited | Esperance | Mobile Voice & Data | Myrup, Bandy Creek, Pink Lake South, Munglinup Camp | WA | The project will deploy three new Telstra macro mobile sites and one new Telstra Small Cell mobile site. The macro sites will deliver improved voice and data connectivity at Myrup, Bandy Creek and Pink lake South and the new small cell will deliver improved voice and data connectivity at Munglinup Camp. | In Progress | Q1, 2025 |
| Telstra Limited | Gingin Transmission Upgrade | Mobile Voice & Data | Gingin and Breera | WA | The project will upgrade one Telstra macro cell base station in Gingin and deploy one new Telstra macro cell base station in Breera, providing coverage to the region and extending coverage to the Brand and Great Northern Highways respectively. | In Progress | Q2, 2025 |
| Telstra Limited | Kununurra | Mobile Voice & Data | Kununurra | WA | The project will deploy one new Telstra macro base station at Kununurra and one Telstra small cell base station at the Frank Wise Institute of Tropical Agriculture, providing new coverage to the area. | In Progress | Q2, 2025 |
| Telstra Limited | Newman | Mobile Voice & Data | Newman | WA | The project will upgrade two Telstra macro cell base stations and deploy one new Telstra macro cell base station and one new Telstra small cell base station to uplift connectivity across Newman and the nearby Aboriginal community of Jigalong. | In Progress | Q2, 2025 |

## Table 3: Regional Connectivity Program Round 3 Project Status

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Grantee | Project Name | Technology Type | Location | State | Project Description | RCP Project Status | Actual / Expected Project Completion Date |
| CiFi Pty Ltd | Norfone NiFi – Norfolk Island Fast Internet | Fixed Wireless Broadband | Norfolk Island | External Territory of Australia | The project will deliver Fixed Wireless broadband, backhauled via satellite, providing coverage to Norfolk Island’s residents. | In Progress | Q1, 2025 |
| Connected Farms Pty Ltd | Weddin Agricultural Precinct | Fixed Wireless Broadband | Weddin | NSW | The project will deliver fixed wireless and mobile broadband, including satellite backhaul, to agricultural areas of Weddin Shire. | In Progress | Q4, 2025 |
| NBN Co Limited | Moulamein Wakool NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Moulamein Wakool | NSW | The project will provide Fixed Wireless broadband to the towns of Moulamein and Wakool. | In Progress | Q2, 2026 |
| Telstra Limited | Central Riverina | Mobile Voice & Data | Ariah Park/Matong | NSW | The project will deliver two new macro mobile base stations providing improved mobile coverage and capacity to Cowabbie and Ariah Park and surrounding areas, including sections of the Newell Highway and Burley Griffin Way. | In Progress | Q2, 2027 |
| Telstra Limited | Curraweela | Mobile Voice & Data | Curraweela | NSW | The project will deliver a new macro mobile base station providing improved mobile coverage and capacity to Curraweela. | In Progress | Q2, 2027 |
| Telstra Limited | Pacific Highway | Mobile Voice & Data | Moorland/Raleigh | NSW | The project will provide two new macro mobile base stations providing improved coverage and capacity along sections of the Pacific Highway at Raleigh and Coopernook, and surrounding areas. | In Progress | Q2, 2027 |
| Telstra Limited | Picnic Point | Mobile Voice & Data | Picnic Point | NSW | The project will deliver a new macro mobile site providing improved mobile coverage and capacity to Picnic Point, near Mathoura NSW. | In Progress | Q2, 2027 |
| Wi-Sky NSW Pty Ltd | Southern NSW Bandwidth Upgrade | Fixed Wireless Broadband | Southern NSW | NSW | The project will upgrade Wi-Sky NSW's existing Fixed Wireless network and backhaul links to increase capacity and speeds in areas across southern NSW. | In Progress | Q4, 2025 |
| YLess4U | High speed Fixed Wireless Broadband access for Urana community | Fixed Wireless Broadband | Urana | NSW | The project will deliver fixed wireless broadband to Urana. | In Progress | Q4, 2025 |
| YLess4U | High speed Fixed Wireless Broadband for Burcher NSW | Fixed Wireless Broadband | Burcher | NSW | The project will provide fixed wireless broadband to Burcher. | In Progress | Q4, 2025 |
| YLess4U | High speed Fixed Wireless Broadband for Burra NSW and Surrounds | Fixed Wireless Broadband | Burra | NSW | The project will provide fixed wireless broadband to Burra. | In Progress | Q4, 2025 |
| YLess4U | High speed Fixed Wireless Broadband for Talbingo NSW | Fixed Wireless Broadband | Talbingo | NSW | The project will provide fixed wireless broadband to Talbingo. | In Progress | Q4, 2025 |
| YLess4U | High speed Fixed Wireless Broadband for Urila NSW and Surrounds | Fixed Wireless Broadband | Urila | NSW | The project will deliver fixed wireless broadband to Urila, NSW | In Progress | Q4, 2025 |
| YLess4U | High speed Fixed Wireless for Eumungerie NSW and Surround | Fixed Wireless Broadband | Eumungerie | NSW | The project will provide fixed wireless broadband to Eumungerie. | In Progress | Q4, 2025 |
| YLess4U | High speed Fixed Wireless for Glen Davis NSW | Fixed Wireless Broadband | Glen Davis | NSW | The project will provide fixed wireless broadband to Glen Davis. | In Progress | Q4, 2025 |
| AARNET | AARNet's high-capacity network connectivity to Batchelor Town | Fibre Broadband | Batchelor | NT | The project will provide 11km of optical fibre connecting the town of Batchelor at key sites including council building, museum, school, community health centre and the Batchelor Institute of Indigenous Tertiary Education. | In Progress | Q4, 2025 |
| Easy Web | Community Wi-Fi – Add managed UPS systems 12 hours autonomy to system headends at nominated Town Camp Community Centres | Satellite Broadband | Anthelk-Ewipaye, Walpiri, Inarlenge, Mpwetyerre and Yarrentyty Arlterre | NT | The project will upgrade Easy Web’s existing Community Wi-Fi services at Anthelk-Ewipaye (Charles Creek), Walpiri, Inarlenge (Little Sisters), Mpwetyerre (Abbots), and Yarrentyty Arlterre (Larapinta Valley) in Alice Springs, installing backup power to increase reliability of service. | Complete | Q4, 2024 |
| Easy Web | Community Wi-Fi – Add solar power systems to 240VAC headends at nominated Town Camps | Satellite Broadband | Aper-Alwerrknge, Akangwertnarre, Lhenpe Artnwe and Mt Nancy's Town Camps | NT | The project will upgrade Easy Web’s existing Community Wi-Fi services at the Aper‑Alwerrknge (Palmer’s), Akangwertnarre (Morris Soak), Lhenpe Artnwe (Hoppy’s) and Mt Nancy town camps in Alice Springs, installing solar-powered batteries to increase reliability of service. | Complete | Q4, 2024 |
| Easy Web | Community Wi-Fi – Solar Headend Solution – Alice Springs Town Camps – Nyewente and Old Times Town Camps | Fixed Wireless Broadband | Nyewente and Old Timers Town Camps (Alice Springs) | NT | The project will provide Wi-Fi and fixed wireless services to the Indigenous town camps of Nyewente and Old Timers at Alice Springs, which will include free Wi-Fi services. | Complete | Q4, 2024 |
| Easy Web | Community Wi-Fi Service Hubs at Wilora, Nturiya, Pmara Jutunta and Mulga Bore Communities, NT | Fixed Wireless Broadband | Wilora, Nturiya, Pmara Jutunta and Mulga Bore | NT | The project will provide Wi-Fi and fixed wireless services to the remote Indigenous communities of Wilora, Nturiya, Pmara Jutunta and Mulga Bore, in the Central Desert Region, which will include free Wi-Fi services. | In Progress | Q1, 2025 |
| Easy Web | Community Wi-Fi Services Hubs at Haasts Bluff, NT | Fixed Wireless Broadband | Haasts Bluff | NT | The project will provide Wi-Fi and fixed wireless services to the Indigenous community of Haasts Bluff, which will include free Wi-Fi services. | Complete | Q4, 2024 |
| NBN Co Limited | Alice Springs NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Alice Springs | NT | The project will deliver fixed wireless broadband to Alice Springs and the surrounding area. | In Progress | Q2, 2026 |
| NBN Co Limited | Katherine NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Katherine | NT | The project will deliver fixed wireless broadband internet to Katherine, replacing the existing NBN Sky Muster service and providing residents with improved reliability, speed and coverage. | In Progress | Q2, 2026 |
| NBN Co Limited | Maningrida NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Maningrida | NT | The project will provide fixed wireless broadband to the Indigenous community of Maningrida. | In Progress | Q2, 2026 |
| Telstra Limited | Amoonguna | Mobile Voice & Data | Amoonguna | NT | The project will provide a small cell mobile site to the Indigenous community of Amoonguna. | In Progress | Q2, 2026 |
| Telstra Limited | Warruwi | Mobile Voice & Data | Warruwi | NT | The project will upgrade the existing Telstra macro site at Warruwi, on South Goulburn Island in the Arafura Sea. | In Progress | Q2, 2026 |
| Australian Private Networks Pty Ltd (Activ8me) | Horn Island Community Wi-Fi and Telephone Service | Satellite Broadband | Horn Island | QLD | The project will provide broadband Wi-Fi internet and telephone connectivity to the remote Indigenous community of Horn Island, including free Wi-Fi connectivity. | In Progress | Q4, 2025 |
| Australian Private Networks Pty Ltd (Activ8me) | Mornington Island Community Wi-Fi and Telephone Service | Satellite Broadband | Mornington Island | QLD | The project will provide broadband Wi-Fi internet and telephone connectivity to the remote Indigenous community of Mornington Island, including free Wi-Fi connectivity. | In Progress | Q4, 2025 |
| Australian Private Networks Pty Ltd (Activ8me) | Wujal Community Wi-Fi and Telephone Service | Satellite Broadband | Wujal Wujal Community, Degarra | QLD | The project will provide broadband Wi-Fi internet and telephone connectivity to the remote Indigenous community of Wujal Wujal in Cape York, including free Wi-Fi connectivity. | In Progress | Q4, 2025 |
| NBN Co Limited | Injune NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Injune | QLD | The project will deliver a tower providing Fixed Wireless broadband to Injune, and surrounding areas. | In Progress | Q2, 2026 |
| NBN Co Limited | Magnetic Island NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Magnetic Island | QLD | The project will deliver fixed wireless broadband to Magnetic Island, providing improved connectivity. | In Progress | Q2, 2026 |
| NBN Co Limited | Palm Island NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Palm Island | QLD | The project will provide fixed wireless broadband to the Indigenous community of Palm Island. | In Progress | Q2, 2026 |
| NBN Co Limited | Torres Strait Islands NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Torres Strait Islands | QLD | The project will provide fixed wireless broadband to islands in the Torres Strait. | In Progress | Q2, 2026 |
| NBN Co Limited | Yarrabah NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Yarrabah | QLD | The project will provide fixed wireless broadband to the Indigenous community of Yarrabah. | In Progress | Q2, 2026 |
| Telstra Limited | Hope Vale West | Mobile Voice & Data | Hope Vale | QLD | The project will deliver a new small cell mobile site providing new coverage and capacity near Hope Vale. | In Progress | Q2, 2026 |
| Telstra Limited | Yarrabah South | Mobile Voice & Data | Yarrabah | QLD | The project will deliver a new macro site providing improved coverage to the Yarrabah Valley including a health centre, school and community aged care centre. | In Progress | Q2, 2027 |
| Wi-Sky Queensland Pty Ltd | Clem Walton Park Connectivity Initiative | Fixed Wireless Broadband | Clem Walton Park | QLD | The project will upgrade Wi-Sky Qld's existing Fixed Wireless infrastructure and install new towers, also providing free limited data Wi-Fi access points, to the area around Clem Walton Park, west of Cloncurry. | In Progress | Q4, 2025 |
| Wi-Sky Queensland Pty Ltd | North West Queensland Gigabit Towns Project | Fixed Wireless Broadband | North West Queensland | QLD | The project will provide fixed wireless connectivity, including limited free public Wi-Fi access at each tower, across a large area of North West Queensland, benefitting communities of Richmond, Julia Creek, Karumba, Normanton and Croydon as well as surrounding properties and farms. | In Progress | Q4, 2025 |
| NBN Co Limited | Coober Pedy NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Coober Pedy | SA | The project will provide fixed wireless broadband to Coober Pedy. | In Progress | Q2, 2026 |
| NBN Co Limited | Lock NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Lock | SA | The project will deliver fixed wireless broadband to Lock, SA, providing improved connectivity. | In Progress | Q2, 2026 |
| Telstra Limited | Limestone Coast | Mobile Voice & Data | Limestone Coast | SA | The project will deliver 27 new mobile sites providing improved connectivity across the Limestone Coast region. | In Progress | Q2, 2027 |
| FortyTwo 24 Pty Ltd | Energising Tullah – Powering connectivity through advanced telecommunications | Fibre Backhaul | Tullah | TAS | The project will deliver a 39km overhead optical fibre extension linking 42-24’s existing optic fibre network to Tullah, upgrading existing backhaul links to increase network capacity. | In Progress | Q4, 2025 |
| FortyTwo 24 Pty Ltd | Unleashing connectivity in Zeehan’s remote realm – Pioneering a path to connected connectivity | Fibre Backhaul | Zeehan | TAS | The project will deliver a 29km optical fibre extension linking 42-24’s existing optic fibre network to Zeehan. | In Progress | Q4, 2025 |
| NBN Co Limited | Fingal NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Fingal | TAS | The project will provide fixed wireless broadband to Fingal. | In Progress | Q2, 2026 |
| Telstra Limited | Dianas Basin-Beaumaris | Mobile Voice & Data | St Helens | TAS | The project will deliver a new macro mobile site, and required backhaul, in the Dianas Basin-Beaumaris region of Northeast Tasmania. | In Progress | Q2, 2027 |
| Telstra Limited | Midland Highway | Mobile Voice & Data | Perth/Oatlands | TAS | The project will provide new and improved coverage along Tasmania’s Midlands highway, with a macro mobile site at Symmons Plains Raceway and a small cell site at St Peters Pass. | In Progress | Q2, 2026 |
| Telstra Limited | Oaks (Quercus Park) | Mobile Voice & Data | Carrick | TAS | The project will provide a new macro mobile site to Oaks/Quercus Park in northern Tasmania. | In Progress | Q2, 2027 |
| NBN Co Limited | Blackwood NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Trentham (Blackwood-Blue Hill Lookout) | VIC | The project will deliver fixed wireless broadband to Blackwood and the surrounding areas of Newbury and Little Hampton, providing improved connectivity. | In Progress | Q2, 2026 |
| NBN Co Limited | Chum Creek NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Chum Creek | VIC | The project will provide fixed wireless broadband to Chum Creek, Victoria. | In Progress | Q2, 2026 |
| NBN Co Limited | Harrietville NBN Satellite to FTTP Access Technology Change | Fibre Broadband | Harrietville | VIC | The project will deliver FTTP to Harrietville, providing residents with improved connectivity. | In Progress | Q2, 2026 |
| NBN Co Limited | Sailors Falls NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Sailors Falls | VIC | The project will deliver fixed wireless broadband to Sailors Falls and surrounding areas in the Hepburn Shire, replacing existing satellite service and providing improved speeds and data. | In Progress | Q2, 2026 |
| Telstra Limited | Bullengarook | Mobile Voice & Data | Bullengarook | VIC | The project will provide a new macro mobile site at Bullengarook in Victoria. | In Progress | Q2, 2027 |
| Telstra Limited | Cavendish | Mobile Voice & Data | Cavendish | VIC | The project will upgrade an existing Telstra small cell in Cavendish to a macro site, providing improved handheld coverage and capacity to the area, including along the Henty Highway. | In Progress | Q2, 2026 |
| Telstra Limited | Echuca Village | Mobile Voice & Data | Echuca Village | VIC | The project will provide a new macro mobile site at Echuca Village on the east side of Echuca. | In Progress | Q2, 2027 |
| Telstra Limited | Kennedys Point | Mobile Voice & Data | Bonnie Doon | VIC | The project will deliver a new macro mobile site at Kennedys Point, located on Lake Eildon in Victoria. | In Progress | Q1, 2027 |
| Telstra Limited | Rokewood | Mobile Voice & Data | Rokewood | VIC | The project will deliver a new Macro Mobile site at Rokewood, providing improved handheld coverage and capacity to the area. | In Progress | Q2, 2027 |
| AARNET | AARNet’s high-capacity Gigabit Network to the North Midlands Shire – Three Springs | Fibre Broadband | Three Springs | WA | The project will provide FTTP connectivity to key premises in Three Springs, including a public library and public school, as well as fixed wireless connectivity to the town. | In Progress | Q4, 2025 |
| AARNET | AARNet's high-capacity Gigabit Network to the North Midlands Shire - Migenew | Fibre Broadband | Migenew | WA | The project will provide FTTP connectivity to key premises in Mingenew, including the public library and public school, as well as fixed wireless connectivity to the town. | In Progress | Q4, 2025 |
| AARNET | AARNet's high-capacity Gigabit Network to the North Midlands Shire - Coorow and Carnamah | Fibre Broadband | Coorow and Carnamah | WA | The project will provide FTTP connectivity to key premises in Coorow and Carnama, including the public libraries and schools, as well as fixed wireless connectivity to the town. | In Progress | Q4, 2025 |
| Australian Private Networks Pty Ltd (Activ8me) | Bidyadanga Community Wi-Fi and Telephone Service | Satellite Broadband | Bidyadanga Community | WA | The project will provide broadband Wi-Fi internet and telephone connectivity to the remote Indigenous community of Bidyadanga, including free Wi-Fi connectivity. | In Progress | Q4, 2025 |
| Australian Private Networks Pty Ltd (Activ8me) | Bidyadanga Outstations | Satellite Broadband | Bidyadanga Outstations | WA | The project will provide broadband Wi-Fi internet and telephone connectivity to 10 remote indigenous outstations surrounding the Bidyadanga community, including free Wi-Fi connectivity. | In Progress | Q4, 2025 |
| Australian Private Networks Pty Ltd (Activ8me) | Burringurrah Community Wi-Fi and Telephone Service | Satellite Broadband | Burringurrah Community | WA | The project will provide broadband Wi-Fi internet and telephone connectivity to the remote Indigenous community of Burringurrah, including free Wi-Fi connectivity. | In Progress | Q4, 2025 |
| Australian Private Networks Pty Ltd (Activ8me) | Guda Guda Community | Satellite Broadband | Guda Guda Community | WA | The project will provide broadband Wi-Fi internet and telephone connectivity to the remote Indigenous community of Guda Guda, including free Wi-Fi connectivity. | In Progress | Q4, 2025 |
| CRISP Wireless Pty Ltd | Narrogin-Wagin Connectivity Expansion | Fixed Wireless Broadband | Narrogin-Waggin | WA | The project will provide Fixed Wireless coverage at 13 sites across the Wheatbelt region of WA. | In Progress | Q4, 2025 |
| CRISP Wireless Pty Ltd | North Coast Next Generation Fixed Wireless | Fixed Wireless Broadband | Northern Wheatbelt Region | WA | The project will provide Fixed Wireless coverage at 11 sites across the Wheatbelt region of WA. | In Progress | Q4, 2025 |
| CRISP Wireless Pty Ltd | Wheatbelt Network Expansion | Fixed Wireless Broadband | Wheatbelt Region | WA | The project will provide Fixed Wireless coverage at 12 sites across the Wheatbelt region of WA. | In Progress | Q4, 2025 |
| NBN Co Limited | Gnowangerup NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Gnowangerup | WA | The project will deliver fixed wireless broadband to the Gnowangerup area of WA. | In Progress | Q2, 2026 |
| NBN Co Limited | Wyndham NBN Satellite to NBN Fixed Wireless Technology Access Change | Fixed Wireless Broadband | Wyndham | WA | The project will provide fixed wireless broadband to the Indigenous community of Wyndham. | In Progress | Q2, 2026 |
| Telstra Limited | Burraluba Yura Ngurra | Mobile Voice & Data | Ord River | WA | The project will provide a new small cell mobile site providing coverage to the Indigenous accommodation facility of Burraluba Yura Ngurra Workers’ Hostel at Halls Creek. | In Progress | Q2, 2026 |
| Telstra Limited | Kurrawang | Mobile Voice & Data | Mount Burges | WA | The project will deliver a new macro mobile site, providing improved handheld coverage and capacity to the Indigenous community of Kurrawang. | In Progress | Q2, 2027 |
| Telstra Limited | Logue Brook Dam | Mobile Voice & Data | Hoffman | WA | The project will provide a new mobile small cell improving coverage and capacity to the Logue Brook Dam area at Hoffman. | In Progress | Q2, 2026 |
| Telstra Limited | Noggerup | Mobile Voice & Data | Mcalinden | WA | The project will deliver a new macro mobile site providing new coverage and capacity to the area near Noggerup and Mcalinden. | In Progress | Q2, 2027 |
| Telstra Limited | Tandegin | Mobile Voice & Data | Tandegin | WA | The project will deliver a new macro mobile site providing new coverage and capacity to the Tandegin area. | In Progress | Q2, 2027 |
| Telstra Limited | Woogenellup | Mobile Voice & Data | Woogenellup | WA | The project will deliver a new macro mobile site providing new coverage and capacity to Woogenellup. | In Progress | Q2, 2027 |